## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 3155/NAD_I | 25/11/2022 | 25/11/2022 | Resource Division | 52.05 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 108/NAD-I | 31/01/2023 | 31/01/2023 | Resource Division | 92.4 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well at Pump House No.-I and II ,Zone-I and New Tube Well at Pump House No.-III, Zone-I in connection to Accommodate FHTC under Gobindapur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-10660] | Assistant Engineer |  | ORD/000644/2024-2025 | 2681/EMD | 20/11/2024 | 20/12/2024 | M/S. G.P. ENTERPRISE | 20.56 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Augmentation work at villages Panchpota, Koehua Para, Bagdia, Beale Danda, Promoth Nagar in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-I at Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000070/2023-2024 | 1379/NAD-I | 15/05/2023 | 14/06/2023 | ALOK ENTERPRISE | 49.8 | 43.95 | 88.25 | 80
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Augmentation of Rising main line at Gobindapur zone-I in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (sL.NO.16) | Assistant Engineer-I | Junior Engineer-II | ORD/000238/2023-2024 | 2301/NAD-I | 29/09/2023 | 14/10/2023 | M/S DIPAK ENTERPRISE | 18.43 | 18.37 | 99.65 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-III | ORD/000065/2022-2023 | 1672 / NAD-I | 07/09/2022 | 06/12/2022 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 329.34 | 61.66 | 70
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Gobindapur, Zone-I W/S Scheme under Santipur Block of capacity 110 cum/hr. under augmentation of Gobindapur, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.06) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-II | ORD/000134/2023-2024 | 1902/NAD-I | 14/08/2023 | 09/11/2025 | MULTITEX ENGINEERING INDUSTRIES | 159.34 | 58.16 | 36.5 | 60
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Retrofitting Pipeline work for providing FHTC (Functional Household Tap Connection) and dedicated line from manifold at Shantipur Block of Ground Water Based PWSS for Gobindapur (Zne-I & II) W/S Scheme inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000271/2023-2024 | 2751/NAD-I | 11/12/2023 | 20/08/2026 | SAHA ENGINEERS | 15.75 | 0 | 0 | 85
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Providing Boundary Illumination with allied works at GOBINDAPUR ZONE-I under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10660) | Assistant Engineer |  | ORD/000151/2025-2026 | 1153/EMD | 04/06/2025 | 02/09/2025 | M/S DAS ENTERPRISE | 4.34 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Pipeline connection from Shonitola more towards Harekrishna more under Jal - Jeevan Mission (JJM) at Shantipur Block of Ground Water based PWSS for Gobindapur Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No.-02) | Assistant Engineer-I | Junior Engineer-II | ORD/000173/2024-2025 | 314/AE-I/NAD-I | 03/12/2024 | 02/01/2025 | MONDAL ENTERPRISE | 0.96 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia | SM/10660 | Augmentation | Interconnection of pipeline from manifold to distribution line for ensuring water at Gobindapur , Mathpara under Gobindapur water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000010/2025-2026 | 112/NAD-I | 21/04/2025 | 19/08/2025 | SAGAR ENTERPRISE | 8.22 | 0 | 0 | 100
Total | [13 empty] | 955.95 | 449.81 | 47.05