## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | FHTC under Jaldhara/Jalswapna for Matikumra Phasa -I at Ranaghat -II Block by augmentation of Ground Water Based PWSS Matikumra Ws scheme under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.05) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000091/2022-2023 | 1938/NAD-I | 12/10/2022 | 10/01/2023 | SATYABRATA CHAKRABORTY | 416.57 | 403.65 | 96.9 | 100
2 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Matikumra ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10661) | Assistant Engineer |  | ORD/000649/2024-2025 | 2686/EMD | 20/11/2024 | 20/12/2024 | M/S DILIP MITRA | 31.76 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Matikumra Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Matikumra (Phase-I) Piped W/S Scheme (Sl.no.20) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000050/2023-2024 | 1449/NAD-I | 26/05/2023 | 10/06/2023 | M/S DIPAK ENTERPRISE | 13.02 | 12.45 | 95.66 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Reconnection at Ukhilnara Chowmatha, laying of pipeline from Ukhilnara Zone-I headwork site to Ukhilnara Chowmatha at Payrandanga G.P in Ukhilnara Zone-I PWSS & Reparing and laying of pipeline at Golabazar ,Matikumra Bazar and 2nd T/W site at Nokari G.P under Jal Jeevan Mission (JJM) for Ranaghat-I & Ranaghat-II Block by retrofitting of Ground Water based PWSS for Matikumra Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000299/2023-2024 | 90/AE-I/NAD-I | 22/02/2024 | 23/03/2024 | GANGULY ENTERPRISE | 3.88 | 3.74 | 96.34 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 10/05/2025 | BALAJI UDDYOG | 129.1 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Augmentation of FHTC and Laying of balanced Pipeline at the command areas of Gayeshpur, Panpara (Part) and Matikumra Mouza under Matikumra Water Supply scheme Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000070/2025-2026 | 531/NAD-I | 03/07/2025 | 01/09/2025 | M/S DIPAK ENTERPRISE | 49.93 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10661 | Augmentation | Providing Boundary Illumination with allied works at Matikumra (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10661) | Assistant Engineer |  | ORD/000154/2025-2026 | 1155/EMD | 04/06/2025 | 02/09/2025 | KASHINATH PAL & CO. | 4.34 | 0 | 0 | 0
Total | [13 empty] | 648.6 | 419.84 | 64.73