## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 20/11/2022 | GHOSH ENTERPRISE | 320.01 | 256.29 | 80.09 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 3005/NAD-I | 04/11/2022 | 04/11/2022 | Resource Division | 22.55 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting work of existing pipelines at Debagram, Ranaghat-II Block in connection with providing FHTC undr JJM under Debagram W/S Scheme under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000072/2023-2024 | 1385/NAD-I | 16/05/2023 | 06/06/2023 | GHOSH ENTERPRISE | 23.15 | 21.9 | 94.6 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Field Level Survey of different School/Anganwadi Centre (AWC) by GPs enabled Mobile Application for uploading of data at IMIS website in Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000220/2023-2024 | 467/AE-I/NAD-I | 09/10/2023 | 30/06/2025 | TECH VISION | 1.15 | 1.08 | 94.53 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Debagram Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Debagram W/S Scheme (Phase-I) under JJM(Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000297/2022-2023 | 719/NAD-I | 27/03/2023 | 11/04/2023 | CHANDAN ROY | 12.95 | 12.52 | 96.72 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Debagram ii)Dhantala iii)Dubli Zone-I iv)Dubli Zone-II v)Zone-IX (Chandmari) vi)Zone-XII (Madanpur) vii)Nabla | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000006/2023-2024 | 168/AE-I/NAD-I | 12/04/2023 | 27/04/2023 | TECH VISION | 4.84 | 4.84 | 100 | 41
7 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting works at Debogramunder Debogram W/S Schemeunder JJM under Ranaghat- II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000147/2023-2024 | 375/AE-II/NAD-I | 29/08/2023 | 05/09/2023 | JYOTIRMOY ENTERPRISE | 3.76 | 3.51 | 93.46 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting work of Debagram, Ranaghat-II Block in connection with providing FHTC under Debagram W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000151/2023-2024 | 2096/NAD-I | 31/08/2023 | 15/09/2023 | UMWELT ENGINEER PVT. LTD. | 23.14 | 22.71 | 98.16 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Renovation of IEP (155m3/hr.) at Debogram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000227/2023-2024 | 2298/NAD-I | 29/09/2023 | 01/02/2025 | M/S DIPAK ENTERPRISE | 15.81 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000354/2023-2024 | 448/AE-I/NAD-I | 29/09/2023 | 29/12/2023 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Surging of existing Tube Well situated at the 3rd Tube Well site at Debogram Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000080/2024-2025 | 205/AE-II/NAD-I | 24/09/2024 | 01/10/2024 | SUMAN CHAKRABORTY | 0.64 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III and IV (Phase-I) under DEBGRAM ground water based water supply scheme under Block_ Ranaghat-II Dist. Nadia under EMD, PHE Dte. (SM/10662) | Assistant Engineer |  | ORD/000641/2024-2025 | 2678/EMD | 20/11/2024 | 20/12/2024 | DEY ENTERPRISE | 41.01 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Laying of additional pipelines and FHTC at south west part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000059/2024-2025 | 1621/NAD-I | 27/09/2024 | 28/03/2025 | M/S A.K. CONSTRUCTION | 68.67 | 11.51 | 16.76 | 75
14 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Laying of additional pipelines and FHTC at north east part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000056/2024-2025 | 1515/NAD-I | 19/09/2024 | 11/01/2026 | MUKHERJEE CONSTRUCTION | 96.45 | 0 | 0 | 75
15 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000038/2024-2025 | 202/AE-I/NAD-I | 28/06/2024 | 28/09/2024 | SUMAN CHAKRABORTY | 4.85 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing FHtC (Functional Household Tap Connection) under Jaldhara/jalswapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I ,PHE Dte |  |  | BILL/00189/2024-2025 | 213/PFMS | 26/09/2024 | 26/09/2024 | GHOSH ENTERPRISE | 13.73 | 0 | 0 | 0
17 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing Boundary Illumination with allied works at Debagram (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10662) | Assistant Engineer |  | ORD/000166/2025-2026 | 1163/EMD | 04/06/2025 | 02/09/2025 | S.S.ENTERPRISES | 4.34 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) |  |  | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 27/06/2025 | GOUTAM DEY | 34.34 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000199/2024-2025 | 18/AE-I/NAD-I | 31/01/2025 | 30/04/2025 | SUMAN CHAKRABORTY | 4.85 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000069/2025-2026 | 530/NAD-I | 03/07/2025 | 01/06/2026 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 78
21 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 08/09/2025 | SUMAN CHAKRABORTY | 96.78 | 0 | 0 | 0
22 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Quotation for new service connection and security deposit for Noapara OHR site (Zone- 3A) |  |  | BILL/02690/2024-2025 | BP-237 | 04/02/2025 | 04/02/2025 | WBSEDCL DEBOGRAM CCC | 7.27 | 0 | 0 | 0
Total | [13 empty] | 858.36 | 339.22 | 39.52