## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting work of existing pipelines at Debagram, Ranaghat-II Block in connection with providing FHTC undr JJM under Debagram W/S Scheme under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000072/2023-2024 | 1385/NAD-I | 16/05/2023 | 06/06/2023 | GHOSH ENTERPRISE | 23.15 | 21.9 | 94.6 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 20/11/2022 | GHOSH ENTERPRISE | 320.01 | 256.29 | 80.09 | 80
3 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Debagram Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Debagram W/S Scheme (Phase-I) under JJM(Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000297/2022-2023 | 719/NAD-I | 27/03/2023 | 11/04/2023 | CHANDAN ROY | 12.95 | 12.52 | 96.72 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Renovation of IEP (155m3/hr.) at Debogram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000227/2023-2024 | 2298/NAD-I | 29/09/2023 | 14/10/2023 | M/S DIPAK ENTERPRISE | 15.81 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Field Level Survey of different School/Anganwadi Centre (AWC) by GPs enabled Mobile Application for uploading of data at IMIS website in Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000220/2023-2024 | 467/AE-I/NAD-I | 09/10/2023 | 07/01/2024 | TECH VISION | 1.15 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 3005/NAD-I | 04/11/2022 |  | Resource Division | 22.55 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting works at Debogramunder Debogram W/S Schemeunder JJM under Ranaghat- II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000147/2023-2024 | 375/AE-II/NAD-I | 29/08/2023 | 05/09/2023 | JYOTIRMOY ENTERPRISE | 3.76 | 3.51 | 93.46 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Retrofitting work of Debagram, Ranaghat-II Block in connection with providing FHTC under Debagram W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000151/2023-2024 | 2096/NAD-I | 31/08/2023 | 15/09/2023 | UMWELT ENGINEER PVT. LTD. | 23.14 | 9.6 | 41.49 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Debagram ii)Dhantala iii)Dubli Zone-I iv)Dubli Zone-II v)Zone-IX (Chandmari) vi)Zone-XII (Madanpur) vii)Nabla | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000006/2023-2024 | 168/AE-I/NAD-I | 12/04/2023 | 27/04/2023 | TECH VISION | 4.84 | 3.97 | 82.01 | 41
10 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000354/2023-2024 | 448/AE-I/NAD-I | 29/09/2023 | 28/12/2023 | SUMAN CHAKRABORTY | 4.85 | 2.42 | 50 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Providing FHtC (Functional Household Tap Connection) under Jaldhara/jalswapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I ,PHE Dte |  |  | BILL/00189/2024-2025 | null | 12/08/2024 |  | GHOSH ENTERPRISE | 13.73 | 0 | 0 | null
12 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000038/2024-2025 | 202/AE-I/NAD-I | 28/06/2024 | 26/09/2024 | SUMAN CHAKRABORTY | 4.85 | 0 | 0 | 0
Total | [13 empty] | 450.77 | 310.22 | 68.82