## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for DUTTAPULIA ZONE-I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-07) | Assistant Engineer-II | Junior Engineer-III | ORD/000207/2021-2022 | 68/AE-II/N.A.D.-I | 24/02/2022 | 26/03/2022 | UMWELT ENGINEER PVT. LTD. | 4.74 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000224/2021-2022 | 69/AE-II/NAD-I | 24/02/2022 | 26/03/2022 | UMWELT ENGINEER PVT. LTD. | 3.5 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Retrofitting work at .Barberia Colony Paschimpara, Dakshinpara, Kushberia, Paschim para Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- I) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (sl.no10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000245/2022-2023 | 570/NAD-I | 16/03/2023 | 06/04/2023 | MONDAL ENTERPRISE | 34.86 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 3005/NAD-I | 04/11/2022 | 04/11/2022 | Resource Division | 14.67 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10663) | Assistant Engineer |  | ORD/000642/2024-2025 | 2679/EMD | 20/11/2024 | 20/12/2024 | GHOSE ENGINEERING SYNDICATE | 32.64 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000094/2022-2023 | 1941/NAD-I | 13/10/2022 | 11/01/2023 | MONDAL ENTERPRISE | 323.87 | 0 | 0 | 95
7 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-I Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-I (Phase-I) under JJM (Sl.no.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000044/2023-2024 | 1365 /NAD-I | 12/05/2023 | 27/05/2023 | M/S ARATI ENTERPRISE | 13.04 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 12/12/2025 | JOYGOPAL GUPTI | 96.49 | 0 | 0 | 57
9 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) |  |  | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 27/06/2025 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Head work site towards Petua and Barberia Mouza in reference to Aranghata and Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000009/2025-2026 | 77/NAD-I | 16/04/2025 | 15/06/2025 | DEBASIS SAMADDAR | 95.65 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10663 | Augmentation | Providing Boundary Illumination with allied works at Duttapulia, Zone-I (Phase-I) under Block_ Ranaghat-II, Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10663) | Assistant Engineer |  | ORD/000167/2025-2026 | 1165/EMD | 04/06/2025 | 02/09/2025 | TAMAL ENTERPRISE | 4.34 | 0 | 0 | 0
Total | [13 empty] | 700.96 | 0 | 0