## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata | SM/11456 | Augmentation | Supplying, ,installation and commissioning of different equipments at the Conference Room under Haringhata WTP to make it compatible for video conferencing facility including supply & installation of surveillance system under Office of the Executive Engineer , Nadia Arsenic Division - I , PHE Dte. under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2022-2023 | 601/NAD-I | 20/04/2022 | 04/06/2022 | ALTAVISTA TECH SOLUTIONS | 24.44 | 0 | 0 | 43
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata | SM/11456 | Augmentation | Charges of entry of household data in JJM with Household Aadhar details ......... Geo Tagging ..... in different Block of Nadia District under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000107/2022-2023 | 163 / AE-I/NAD-I | 04/07/2022 | 02/10/2022 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata | SM/11456 | Augmentation | Repair of 450 cum capacity Over Head Reservoir, for Chakdah WTP under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 08) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000057/2022-2023 | 1637 / NAD-I | 06/09/2022 | 21/10/2022 | M/S R.K. ENTERPRISE | 13.75 | 11.47 | 83.36 | 55
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata | SM/11456 | Augmentation | Providing FHTC Functional Household Tap Connection under Jal Jeevan Mission JJM Zone -V Darrappur Part -IV at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata and Chakdah Part W/S Scheme under Nadia Arsenic Division- I P.H.E Dte. (Sl. No. 17) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-IV | ORD/000128/2022-2023 | 3041/NAD-I | 09/11/2022 | 24/12/2022 | M/S DIPAK ENTERPRISE | 71.77 | 70.32 | 97.98 | 80
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata | SM/11456 | Augmentation | Road Restoration under Jal Jeevan Mission (JJM) for Birohi-I and Fatepur G.P. and Haringhata Block under Providing FHTC (Functional Househod Tap Connection) under Jaldhara/Jalswapna for Zone-III (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000081/2025-2026 | 582/NAD-I | 10/07/2025 | 08/09/2025 | SUMAN CHAKRABORTY | 10.33 | 0 | 0 | 100
Total | [13 empty] | 125.15 | 86.64 | 69.23