## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 15/01/2025 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-I, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000233/2023-2024 | 497/AE-I/NAD-I | 31/10/2023 | 07/11/2023 | DAYANIDHI CONSTRUCTIONS | 0.97 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-II, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000234/2023-2024 | 498/AE-I/NAD-I | 31/10/2023 | 07/11/2023 | M/S T.S. ENTERPRISE | 0.95 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Muragachha Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Arsenic Division-I,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Muragachha Zone-I & Zone-II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000023/2024-2025 | 1135/NAD-I | 24/07/2024 | 22/09/2024 | GHOSH & CO | 17.57 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Augmentation of Muragaccha Zone - I PWSS by providing dedicated pipeline under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(Sl. No. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000169/2024-2025 | 2040/NAD-I | 06/12/2024 | 01/05/2025 | MESSRS FREEDOM CONSTRUCTION | 95.13 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Providing FHTC under Jalswapna / Jaldhara for Muragachha Z-I & II ( Part -III) at Hanskhali Block by Augmentation of Ground Water based pipe PWSS for Muragachha W/S Scheme. under Nadia Arsenic Division -I, P.H.E. Dte. (Sl .no. 06) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000124/2022-2023 | 2050 / NAD-I | 21/10/2022 | 29/01/2025 | MONDAL PRECISION PRIVATE LIMITED | 282.77 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Murgachha Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under 1304536.00 26091.00 Initially Nil, Rs. 1005/- per copy of tender document including 2911(ii) to be purchased by the successful bidder at 15 Days Page 3Muragachha Zone-I & II (Part-III) Piped W/S Scheme (sl.16) | Assistant Engineer-II | Junior Engineer-IV | ORD/000024/2023-2024 | 1160 / NAD-I | 28/04/2023 | 01/05/2025 | SANJIB DEY | 13.05 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Muragachha, Zone-I W/S Scheme under Hanskahli Block of capacity 65 cum/hr. under augmentation of Muragachha, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000145/2023-2024 | 2046/NAD-I | 24/08/2023 | 16/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 132.46 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi | SM/11640 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Muragachha Zone-II W/S Scheme under Hanskhali Block of capacity 75 cum/hr. under augmentation of Muragachha Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000142/2023-2024 | 2043/NAD-I | 24/08/2023 | 16/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 144.1 | 0 | 0 | 100
Total | [13 empty] | 952.02 | 0 | 0