## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Baganchra under Ground Water Based PWSS for Baganchra Water Supply Scheme at Santipur Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000036/2022-2023 | 221/AE-I/NAD-I | 02/09/2022 | 02/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 4.78 | 100 | 100
2 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Structural stability report for repair/reconstruction of existing overhead reservoir at Baganchara Water Supply Scheme. |  |  | BILL/00483/2023-2024 | 379/PFMS | 06/12/2023 |  | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 59/NAD-I | 16/01/2024 |  | Resource Division | 30.8 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Surging of existing Tube Well Situated at Head Site of Baganchara Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000304/2023-2024 | 69/AE-I/NAD-I | 12/02/2024 | 27/02/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.64 | 0.32 | 50 | 100
5 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000024/2024-2025 | 1079/NAD-I | 15/07/2024 | 11/01/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | DI Rising main line at Baganchara PWSS under Santipur Block in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. |  | Junior Engineer-II | ORD/000030/2024-2025 | 232/AE-I/NAD-I | 25/07/2024 | 09/08/2024 | MANARAMA ENTERPRISE | 3.96 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site for Baganchara Piped Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000040/2024-2025 | 1314/NAD-I | 22/08/2024 | 21/10/2024 | K K MARKETING | 13.01 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | SM/12018 | Augmentation | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE(PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall, Chlorine Room, and Approach Road (60.0m Length and 3.0m Wide) and Toilet at Head Work Site and 2nd T/W Site and Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Ground Water Based Piped Water Supply Scheme for Baganchara in Santipur Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II | ORD/000128/2023-2024 | 1896/NAD-I | 14/08/2023 | 08/08/2024 | KINGS AND CO | 706.54 | 73.49 | 10.4 | 22
Total | [13 empty] | 1040.45 | 78.59 | 7.55