## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Construction of Boundary Wall, Toilet , Pathway and other allied works at Bhayana Z-I W/S Scheme within Hanshkhali Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.No. 20) | Assistant Engineer-II | Junior Engineer-IV | ORD/000046/2022-2023 | 1586 / NAD-I | 06/09/2022 | 21/10/2022 | CHANDAN ROY | 13.37 | 12.05 | 90.15 | 100
2 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 300mtrs Depth ) by utilising Departmental Machineries for Bhayna W/S Scheme(Z-II)Ranaghat-I Block under Nadia District ,CDD,PHE Dte. | Driller In Charge | Junior Engineer | ORD/000454/2022-2023 | 1826/CDD | 06/01/2023 | 05/02/2023 | M/S SAIKAT ENTERPRISE | 15.55 | 10.73 | 69 | 100
3 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 79/S&WSD | 27/07/2023 | 25/09/2023 | NAGENDRA PATRA | 0.44 | 1.07 | 244.37 | 33
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1961/NAD-I | 18/08/2023 | 18/08/2023 | Resource Division | 12.32 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | New Service connection at bagula under Bhayna W/S Scheme. |  |  | BILL/03358/2023-2024 | BP-211-23-24 | 17/10/2023 | 17/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.15 | 0 | 0 | 0
6 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000183/2023-2024 | 164/S&WSD | 19/12/2023 | 19/06/2024 | NAGENDRA PATRA | 0.86 | 2.26 | 261.82 | 63
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-I GroundWater Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation in connection with JJM under Bhayna Zone-I & Zone-II Part-III Piped W/S Scheme (Sl.no28) | Assistant Engineer-II | Junior Engineer-IV | ORD/000047/2023-2024 | 1451/NAD-I | 26/05/2023 | 10/06/2023 | PALCON | 12.98 | 12.9 | 99.4 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Bhayna Zone-I & Zone-II (Part-III) Piped W/S Scheme (Sl.no.29) | Assistant Engineer-II | Junior Engineer-IV | ORD/000042/2023-2024 | 1361 /NAD-I | 12/05/2023 | 27/05/2023 | NISHITH BANERJEE | 13.04 | 13.01 | 99.78 | 100
9 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Continuation for hiring of Diesel driven Motor Cab(BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 117/S&WSD | 30/10/2023 | 30/12/2023 | NAGENDRA PATRA | 0.29 | 0.74 | 255.17 | 50
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 02/11/2024 | B.S. ENTERPRISE | 19.54 | 11.43 | 58.49 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Supply, delivery and storage at site of automatically controlled diapharm type Chlorinatore dosing pump. Under Augmentation of Ground Water Based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000003/2024-2025 | 141/AE-II/NAD-I | 07/06/2024 | 07/07/2024 | MANARAMA ENTERPRISE | 2.89 | 2.89 | 100 | 100
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 8.62 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhayna Zone-I & II Part-III at Hanskhali block by Augmentation of Ground water based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-I | ORD/000095/2023-2024 | 1686/NAD-I | 12/07/2023 | 09/09/2025 | TAPU SAHA | 390.82 | 113.4 | 29.01 | 80
14 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/12019 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Bhayna Zone-I W/S Scheme under Hanskhali Block of capacity 125 cum/hr. under augmentation of Bhayna Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000143/2023-2024 | 2044/NAD-I | 24/08/2023 | 22/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 165.95 | 106.21 | 64 | 94
Total | [13 empty] | 657.83 | 286.69 | 43.58