## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR HALALPUR-KRISHNAPUR W/S SCHEME (Z-I), RANAGHAT BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000395/2022-2023 | 1451/CDD | 30/11/2022 | 30/12/2022 | M/S SAIKAT ENTERPRISE | 15.55 | 10.4 | 66.83 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Kharida Chapra Primary School to Purba Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Retrofitting of Ground Water Based PWSS of Halalpur- Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000218/2022-2023 | 100/AE-I/NAD-i | 20/02/2023 | 07/03/2023 | MONDAL ENTERPRISE | 3.56 | 3.56 | 100 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Halalpur-Krishnapur Zone-I & II (Part-III) Piped W/S Scheme (sl.19) | Assistant Engineer-II | Junior Engineer-III | ORD/000025/2023-2024 | 1161 / NAD-I | 28/04/2023 | 13/05/2023 | B.S. ENTERPRISE | 13.04 | 12.61 | 96.72 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1961/NAD-I | 18/08/2023 | 18/08/2023 | Resource Division | 15.4 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM), Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work Site & 2nd T/W Site, Repair of 350 cum capacity Over Head Reservoir, Painting and Pump House at Halalpur Krishnapur Zone-I & Repair of 180 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House at Halapur Zone-II for Halalpur Krishnapur Zone-I & II at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000098/2023-2024 | 1742/NAD-I | 19/07/2023 | 17/10/2023 | SATYABRATA CHAKRABORTY | 377.65 | 64.63 | 17.11 | 40
6 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 1601/EMD | 26/04/2023 | 26/05/2023 | M/S DILIP MITRA | 56.44 | 18.77 | 33.26 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Muragachha Zone-I & II (Part-III) Piped W/S Scheme (Sl.no.18) | Assistant Engineer-II | Junior Engineer-III | ORD/000051/2023-2024 | 1430/NAD-I | 24/05/2023 | 08/06/2023 | D.K. CONSTRUCTION | 12.98 | 12.38 | 95.39 | 100
8 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Providing Boundary Illumination with allied works at Halalpur Krishnapur Zone-I and Zone II Part III under Block_ Ranaghat II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12020) | Assistant Engineer |  | ORD/000152/2025-2026 | 1154/EMD | 04/06/2025 | 02/09/2025 | KASHINATH PAL & CO. | 8.68 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) |  |  | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 27/06/2025 | TAPU SAHA | 86.49 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N | SM/12020 | Augmentation | Interconnection of M.S pipeline with Manifold at Halalpur Krishnapur Z-1 Water Supply Scheme including fixing of Sign Board for dematcation of Land at different location under the judisdiction of Nadia Arsenic Division-I ,PHE Dte. under JJM. (Sl. No. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000034/2025-2026 | 168/NAD-I | 29/04/2025 | 28/06/2025 | BUDDHADEV MONDAL | 9.81 | 0 | 0 | 60
Total | [13 empty] | 599.6 | 122.35 | 20.41