## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction of Approach Road and allied work at site of Arranghata Z-I W/S scheme within Ranaghat -II Block under Nadia Arsenic Division -I ( Sl.no. 01) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000045/2022-2023 | 1585 / NAD-I | 06/09/2022 | 21/10/2022 | B.K. ENGINEERING | 12.4 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2023-2024 | 1155 / NAD-I | 28/04/2023 | 13/05/2023 | BISWAS ENTERPRISE | 13.04 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) at Jugolkishore G.P. under Jal Jeevan Mission (JJM) for Ranaghat-II Block of Goalsalua Zone-I Ground Water based PWSS under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000298/2023-2024 | 167/NAD-I | 07/02/2024 | 22/02/2024 | GOUTAM DEY | 4.91 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 20/11/2022 | GHOSH ENTERPRISE | 320.01 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-I W/S Scheme under JJM (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000018/2023-2024 | 1154 / NAD-I | 28/04/2023 | 13/05/2023 | BUDDHADEV MONDAL | 13.02 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone-I (Phase-II) W/S Scheme under JJM (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000054/2023-2024 | 1425/NAD-I | 23/05/2023 | 07/06/2023 | M/S BISWAS BROTHERS | 12.98 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Paschim Noapara Ground Based Water Supply Scheme under Ranaghat-I, under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Paschim Noapara Water Supply Scheme under JJM (Sl.No.-04) | Assistant Engineer-I | Junior Engineer-I | ORD/000294/2022-2023 | 720/NAD-I | 27/03/2023 | 11/04/2023 | DAS CONSTRUCTION | 13.04 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Retrofitting work at Chandpur More area under Ranaghat-II block Augmentation of Ground Water Based PWSS for Dhantala W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000146/2023-2024 | 369/AE-II/NAD-I | 24/08/2023 | 31/08/2023 | REKHA ENTERPRISE | 2.31 | 0 | 0 | 60
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Retrofitting work under Jal Jeevan Mission (JJM) for Gourisail area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS forDubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.22) | Assistant Engineer-II | Junior Engineer-III | ORD/000192/2023-2024 | 2207/NAD-I | 13/09/2023 | 13/10/2023 | GHOSH ENTERPRISE | 95.24 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Retrofitting work including FHTC (Functional Household Tap Connection) of Garapota and Duttaphulia at Block Hanskhali under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000215/2023-2024 | 2253/NAD-I | 22/09/2023 | 13/10/2023 | M/S A.K. CONSTRUCTION | 78.25 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Culvert crossing and restoration of pipeline including jointing with manifold and other allied works under Paschim Noapara Water Supply Scheme , Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000055/2024-2025 | 1555/NAD-I | 25/09/2024 | 09/11/2024 | JOYGOPAL GUPTI | 6.11 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 01/04/2025 | DIVINE | 329.47 | 0 | 0 | 75
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Providing FHTC and laying dedicated pipeline for Uzirpukuria, Humaniapota, Purba Simulia Village under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000037/2025-2026 | 248/NAD-I | 15/05/2025 | 14/07/2025 | SUMAN CHAKRABORTY | 58.02 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) |  |  | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 21/06/2025 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0 | 0
15 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-II Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone- II (Phase-I) under JJM (sl.06) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000020/2023-2024 | 1157/NAD-I | 28/04/2023 | 25/04/2025 | BISWAS CONSTRUCTION | 13.01 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | Retrofitting work under Jal Jeevan Mission (JJM) for Humanipota & Kamargaria area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Dubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000267/2023-2024 | 2689/NAD-I | 05/12/2023 | 04/02/2025 | TARUN GHOSH | 56.47 | 0 | 0 | 70
17 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta | SM/12022 | Augmentation | "Augmentation of Garapota PWSS by providing dedicated pipeline for Shibchandrapur and Kutaknagar mouza under Nadia Arsenic Division-I,P.H.E. Dte. as a part of Jal Jeevan Mission.(SL. No. 07)" | Assistant Engineer-II | Junior Engineer-IV | ORD/000140/2024-2025 | 2007/NAD-I | 29/11/2024 | 10/04/2025 | BUDDHADEV MONDAL | 57.81 | 0 | 0 | 80
Total | [13 empty] | 1138.52 | 0 | 0