## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting work at Radhakantapur Mouza at Ranaghat-I Block by augmentation of Ground Water based PWSS of Radhakantapur water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000106/2022-2023 | 2053/NAD-I | 21/10/2022 | 05/12/2022 | M/S DIPAK ENTERPRISE | 61.28 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atRanaghat-I Block underRdahakantapur PWSS underAugmentation of Ground Water Based Water SupplyScheme of Tarapur, Kalaighata, Radhakantapur, Praniamatpur & Birnagar Part-III at Ranaghat-I Block (sl.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000212/2022-2023 | 204 /NAD-I | 15/02/2023 | 08/03/2023 | SATYABRATA CHAKRABORTY | 33.07 | 0 | 0 | 35
3 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TARAPUR W/S SCHEME, RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000406/2022-2023 | 1825/CDD | 06/01/2023 | 05/02/2023 | M/S SAIKAT ENTERPRISE | 15.55 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting works at Paharpur Mouza at Ranaghat-I Block by augmentation of Ground Water Based PWSS of Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000125/2022-2023 | 3038/NAD-I | 09/11/2022 | 24/12/2022 | BISWAS CONSTRUCTION | 9.17 | 0 | 0 | 100
5 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under RADHAKANTAPUR W/S Scheme, Block-RanaghatII , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No. - 06) | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 1605/EMD | 26/04/2023 | 26/05/2023 | SWAPAN KUMAR BHANJA | 19.21 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Jackpushing of pipeline at Sahidpally and different Augmentation work of Radhakantapur, Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by Augmentation of Ground Water Based Piped Water Supply Scheme for Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.n.08) | Assistant Engineer-I | Junior Engineer-I | ORD/000161/2023-2024 | 2119/NAD-I | 04/09/2023 | 25/09/2023 | M/S DIPAK ENTERPRISE | 65.68 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Jackpushing of pipeline between Majherchar and Sahidpally and different Augmentation works of Tarapur and Kalaighata Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by augmentation of Ground Water based PWSS for Tarapur & Kalaighata under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.13) | Assistant Engineer-I | Junior Engineer-I | ORD/000164/2023-2024 | 2122/NAD-I | 04/09/2023 | 25/09/2023 | M/S DIPAK ENTERPRISE | 96.43 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Shifting and Laying of Pipeline under Jal Jeevan Mission (JJM) for Ganguly Para, Chatterjee Para and Augmentation works of Parniamatpur by Augmentation of Ground Water based PWSS for Parniamatpur Water Supply Scheme, Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.07) | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2023-2024 | 2116/NAD-I | 04/09/2023 | 25/09/2023 | BUDDHADEV MONDAL | 17.56 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR(Z-I), PAR-NIAMATPUR W/S Scheme, Block- Ranaghat-II , Dist. - Nadia NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 1602/EMD | 26/04/2023 | 26/05/2023 | PADMA ENGINEERING CO. | 38.83 | 0 | 0 | 50
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Par Niamatpur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Parniamatpur Part-III Piped W/S Scheme (Sl.no.26) | Assistant Engineer-I | Junior Engineer-I | ORD/000049/2023-2024 | 1450/NAD-I | 26/05/2023 | 10/06/2023 | SAORSA | 13.01 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Radhakantapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Radhakantapur Part-III Piped W/S Scheme (Sl.no.25) | Assistant Engineer-I | Junior Engineer-I | ORD/000100/2023-2024 | 1689/NAD-I | 12/07/2023 | 27/07/2023 | KESHOB ENTERPRISE | 13.04 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Part-III at Ranaghat-I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Water Supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Tarapur water supply scheme. Repair of Pump House & other units of AIRP and other allied works at Kalaighata water supply scheme Construction of Boundary wall, Toilet, Pathway and other allied work at Kalaighata Water supply Scheme, Repair of Pump House and construction of Boundary Wall and other allied works at Radhakantapur water supply scheme, Repair of Over Head Reservoir and other allied works at Radhakantapur water supply scheme, Construction of Boundary wall, Toilet, Pathway andother allied work at Parniamatpur Water supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Parniamatpur water supply scheme, Repairing,Painting of Boundary wall,Toilet,Pathway and other allied works at Birnagar water supply scheme, Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House and AIRP at Birnagar water supply scheme, under Nadia Arsenic Division-I, PHEDte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000101/2023-2024 | 1698/NAD-I | 13/07/2023 | 12/07/2024 | M/S DIPAK ENTERPRISE | 481.09 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Laying of UPVC pipeline and other allied works near House of Richa Master at Uttarpara Tarapur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000169/2023-2024 | 423/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | ASHIM ENTERPRISE | 3.72 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works at Parniamatpur Mouza under JJM by Augmentation of Ground Water Based PWSS of Parniamatpur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000174/2023-2024 | 422/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | M/S RANA ENTERPRISE | 3.16 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Laying of UPVC pipelineat Uttarpara Tarapur Mouza by retrofitting of GRound Water Based PWSS under JJM at Ranaghat-I block by augmentation of Tarpur Part-III W/S Scheme under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000175/2023-2024 | 424/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | KUHELI ENTERPRISE | 4.82 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Laying of UPVC pipeline at Gazipur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000176/2023-2024 | 425/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | DAFADAR ENTERPRISE | 4.84 | 0 | 0 | 100
17 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Lyaing of UPVC Pipeline at Sureshnagar, Tarapur Mouza by retrofitting of Ground Water Based PWSS under JJM at Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000177/2023-2024 | 426/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | SAGAR ENTERPRISE | 4.81 | 0 | 0 | 100
18 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works near Colony Para Bridge at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic | Assistant Engineer-I | Junior Engineer-I | ORD/000180/2023-2024 | 420/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | M/S PHANINDRA NATH ROY | 4.32 | 0 | 0 | 100
19 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works from Kalaighata Kheyaghat to Mathpara Kali Mandir at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000173/2023-2024 | 421/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | MANARAMA ENTERPRISE | 4.66 | 0 | 0 | 100
20 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Augmentation Work under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata and Parniamatpur PWSS Part- III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata and Parniamatpur Water Supply Schemes under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000190/2023-2024 | 2205/NAD-I | 13/09/2023 | 08/10/2023 | M/S R.K. ENTERPRISE | 7.09 | 0 | 0 | 100
21 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works near House of Saroda Nath at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000171/2023-2024 | 419/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | MRINAL DASGUPTA | 4.76 | 0 | 0 | 100
22 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 9.86 | 0 | 0 | 0
23 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Augmentation of distribution pipeline at Gazipur & Tarapur Mouzas including balance FHTC connections at Tarapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 10) | Assistant Engineer-I | Junior Engineer-I | ORD/000122/2024-2025 | 1924/NAD-I | 22/11/2024 | 08/10/2025 | BISWAS CONSTRUCTION | 19.11 | 0 | 0 | 80
24 | NADIA |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Providing Boundary Illumination with allied works at Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III under Block_ Ranaghat -I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12023) | Assistant Engineer |  | ORD/000162/2025-2026 | 1160/EMD | 04/06/2025 | 02/09/2025 | PIONEER ELECTRICALS | 21.71 | 0 | 0 | 0
25 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan | SM/12023 | Augmentation | Augmentation of FHTC and Laying of balanced Pipeline at Gazipur, Tarapur, Girish Nagar, Jhau Mahal, Suresh Nagar under Tarapur GP at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000079/2025-2026 | 580/NAD-I | 10/07/2025 | 08/09/2025 | BISWAS CONSTRUCTION | 27.98 | 0 | 0 | 0
Total | [13 empty] | 984.78 | 0 | 0