## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Preparation of Detailed Project Report (DPR) for Gosair Char Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000166/2022-2023 | 3286 /NAD-I | 08/12/2022 | 15/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 2.92 | 2.87 | 98.26 | 100
2 | NADIA | Ranaghat-I | Eastern Mechanical | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for New Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gosai Char ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. [SM/13758] | Assistant Engineer |  | ORD/000645/2024-2025 | 2682/EMD | 20/11/2024 | 20/12/2024 | WESTERN ENGINEERING CO. | 21.26 | 0 | 0 | 0
3 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 3.09 | 0 | 0 | 0
4 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 845/NAD-I | 04/06/2024 | 04/06/2024 | Resource Division | 1.87 | 0 | 0 | 0
5 | NADIA | Ranaghat-I | Eastern Mechanical | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | New Service Connection for Gosaichar Water supply scheme |  |  | BILL/02312/2024-2025 | BP-197-24-25 | 17/12/2024 | 17/12/2024 | W.B.S.E.D.C.L (AISHTAL CCC) | 4.98 | 0 | 0 | 0
6 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | "Augmentation of pipeline damaged due to construction of drain including new pipeline and FHTC connection at Sundalpur Char, Paschim Noapara, Sahebdanga, Paschim Noapara villages under Paschim Noapara PWSS and Gosaichar village under Gosaichar Water Supply Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (S1. No. 01)" | Assistant Engineer-I | Junior Engineer-I | ORD/000139/2024-2025 | 2005/NAD-I | 29/11/2024 | 28/05/2025 | M/S DIPAK ENTERPRISE | 24.76 | 0 | 0 | 100
Total | [13 empty] | 58.88 | 2.87 | 4.88