## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Preparation of Detailed Project Report (DPR) for Birnagar (Part) Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.01) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000167/2022-2023 | 3287 / NAD-I | 08/12/2022 | 15/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.74 | 3.65 | 97.52 | 100
2 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Augmentation work of 2 no Gobindanagar near Indira More & Birnagar at Ranaghat-I Block under augmentation of Ground Water Based PWSS of Birnagar Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.16) | Assistant Engineer-I | Junior Engineer-I | ORD/000165/2023-2024 | 2123/NAD-I | 04/09/2023 | 25/09/2023 | CHOWDHURY & CO. | 75.32 | 75.22 | 99.87 | 100
3 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & Valves & Pipe supporting Structure, Construction of 100 cum capacity 20 mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials, Construction of Boundary Wall [H/W Site (160.0 m length), 2nd T/W Site(45.0 length)], Pump House for H/W Site (4.88 M X 3.60 M), 2nd T/W Site (3.60 M X 3.0 M), Land Development, Restoration of Bituminous Road and allied works with Approach Road (105.0 m length and 3.0m wide), Soil Investigation for the work of Construction of RCC Elevated Reservoir of capacity 100 M3 Staging Height 20 mtr. and Restoration Work for Bituminous Road at Ground Water Based Piped W/S Scheme for Birnagar (Part) in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000093/2023-2024 | 1741/NAD-I | 19/07/2023 | 01/10/2026 | M/S MALLICK ENTERPRISE | 341.12 | 45.03 | 13.2 | 75
4 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for at Madanpur-I & II G.P. and different augmentation works of Radhakantapur and Birnagar Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I block by augmentation of Ground Water Based PWSS for Radhakantapur and Birnagar under Nadia Arsenic Division-I, PHE Dte. (Sl.no.11) | Assistant Engineer-I | Junior Engineer-I | ORD/000162/2023-2024 | 2120/NAD-I | 04/09/2023 | 25/09/2023 | CHOWDHURY & CO. | 96.13 | 79.5 | 82.7 | 70
5 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 846/NAD-I | 04/06/2024 | 04/06/2024 | Resource Division | 1.52 | 0 | 0 | 0
6 | NADIA | Ranaghat-I | Eastern Mechanical | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Providing Boundary Illumination with allied works at Birnagar (Part) under Block_ Ranaghat-I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14196) | Assistant Engineer |  | ORD/000163/2025-2026 | 1161/EMD | 04/06/2025 | 02/09/2025 | WESTERN ENGINEERING CO. | 4.31 | 0 | 0 | 0
Total | [13 empty] | 522.15 | 203.4 | 38.95