## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Preparation of Detailed Project Report (DPR) for Birnagar (Part) Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.01) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000167/2022-2023 | 3287 / NAD-I | 08/12/2022 | 15/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.74 | 0 | 0 | 100
2 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Augmentation work of 2 no Gobindanagar near Indira More & Birnagar at Ranaghat-I Block under augmentation of Ground Water Based PWSS of Birnagar Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.16) | Assistant Engineer-I | Junior Engineer-I | ORD/000165/2023-2024 | 2123/NAD-I | 04/09/2023 | 25/09/2023 | CHOWDHURY & CO. | 75.32 | 0 | 0 | 100
3 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for at Madanpur-I & II G.P. and different augmentation works of Radhakantapur and Birnagar Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I block by augmentation of Ground Water Based PWSS for Radhakantapur and Birnagar under Nadia Arsenic Division-I, PHE Dte. (Sl.no.11) | Assistant Engineer-I | Junior Engineer-I | ORD/000162/2023-2024 | 2120/NAD-I | 04/09/2023 | 18/08/2025 | CHOWDHURY & CO. | 96.13 | 0 | 0 | 70
4 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 846/NAD-I | 04/06/2024 | 04/06/2024 | Resource Division | 1.52 | 0 | 0 | 0
5 | NADIA | Ranaghat-I | Eastern Mechanical | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Providing Boundary Illumination with allied works at Birnagar (Part) under Block_ Ranaghat-I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14196) | Assistant Engineer |  | ORD/000163/2025-2026 | 1161/EMD | 04/06/2025 | 02/09/2025 | WESTERN ENGINEERING CO. | 4.31 | 0 | 0 | 0
6 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14196 | New | Dedicated pipeline towards Durgapur Mouza and adjacent areas including allied works for Birnagar PWSS at Ranaghat-I Block of Ground Water Based PWSS for Birnagar W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000135/2024-2025 | 1966/NAD-I | 28/11/2024 | 27/01/2025 | M/S DIPAK ENTERPRISE | 82.96 | 0 | 0 | 100
Total | [13 empty] | 263.99 | 0 | 0