## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Preparation of Detailed Project Report (DPR) for Raynagar Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000168/2022-2023 | 3288 / NAD-I | 08/12/2022 | 15/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 8.5 | 8.41 | 99.01 | 100
2 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Providing, Laying of Rising Main, Laying Distribution system and FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr. Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials and construction of Pump house, Boundary Wall, Service and allied Works at head work & 2nd site at Raynagar Zone-II under Jal Jeevan Mission for Raynagar Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000109/2023-2024 | 1765/NAD-I | 24/07/2023 | 24/07/2024 | MINTU CHAKRABORTY | 337.06 | 0 | 0 | 0
3 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | "Providing Laying of Rising Main ,Laying distribution system and FHTC Soil investigation for the work of construction of 200 cum OHR staging heigjt 20 mtr , Construction of 200 cum capacity 20 mtr . staging hieght RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house , Boundary Wall , Service and Allied Works at head work & 2nd site under Jal Jivan Mission for Raynagar Zone -II Water Supply Scheme within Ranaghat -I Block under Nadia Arsenic Division -I P.H.E.Dte." (Sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000209/2023-2024 | 2292/NAD-I | 27/09/2023 | 26/09/2025 | TAPU SAHA | 386.21 | 0 | 0 | 70
4 | NADIA | Ranaghat-II | Eastern Mechanical | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I and II (Zone-I and II) under Raynagar ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/14234) | Assistant Engineer |  | ORD/000653/2024-2025 | 2690/EMD | 20/11/2024 | 20/12/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 46.24 | 0 | 0 | 0
5 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 8.49 | 0 | 0 | 0
6 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Duttaphulia-Aranghata Road from CH. 35.00 Km. to CH. 40.00 Km. Restoration estimate due to excavations for underground Water Supply pipeline by Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00200/2024-2025 | 222/PFMS | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 60.83 | 0 | 0 | 0
7 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Nokari- Aishmali Road from CH. 2.95 Km. to CH. 6.20 Km. Restoration work arising out of damage of black top for laying of pipe line for "Integrated surface water besed PWSS for Ranaghat -I and Ranaghat -II, Block by Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00199/2024-2025 | 221/PFMS | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 62.96 | 0 | 0 | 0
8 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Duttaphulia-Aranghata Road from CH. 40.00 Km. to CH. 44.766 Km. Restoration estimate due to the cause of excavations for underground Water Supply pipeline layout Proposal of PHE along the R/S of Quality Control sub-Division-I, under Nadia Highway Division-I, in the District Nadia during 2023-2024. |  |  | BILL/00409/2024-2025 |  | 18/12/2024 | 18/12/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 64.84 | 0 | 0 | 0
9 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 21/06/2025 | CHOWDHURY & CO. | 96.3 | 0 | 0 | 0
10 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Work for revamping / upgradation of the hydraulic parameters of distribution network in reference to Raynagar and Joypur W/S Scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000008/2025-2026 | 75/NAD-I | 16/04/2025 | 17/09/2026 | S B CONSTRUCTION | 57.7 | 0 | 0 | 75
11 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) |  |  | ORD/000254/2024-2025 | 17/AE-1/NAD-I | 31/01/2025 | 31/07/2025 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
12 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) |  |  | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 27/06/2025 | TAPU SAHA | 86.49 | 0 | 0 | 0
13 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Balance Work for revamping / upgradation of the hydraulic parameters of distribution network towards Badkulla in reference to Raynagar and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000020/2025-2026 | 138/NAD-I | 23/04/2025 | 18/08/2026 | BUDDHADEV MONDAL | 95.86 | 0 | 0 | 0
14 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Balance Work to complete revamping/upgradation of the hydraulic parameters at distribution network at the part of Betna Mouza and Raynagar Mouza in reference to Raynagar PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (2nd Call) (Sl. NO. 02) |  |  | ORD/000138/2025-2026 | 1043/NAD-I | 25/09/2025 | 23/01/2026 | M/S A.K. CONSTRUCTION | 61.71 | 0 | 0 | 0
15 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Repair of different types road under Majhergram, Kamalpur GP Duttaphulia GP, Nokari GP Jugolkisore GP, Arranaghata GP Bahirgachi GP under Raynagar W/S under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000014/2025-2026 | 130/NAD-I | 22/04/2025 | 22/05/2025 | GHOSH ENTERPRISE | 29.51 | 0 | 0 | 100
16 | NADIA | Ranaghat-II | Eastern Mechanical | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | NEW SERVICE CONNECTION CHARGES FOR RAYNAGAR ZONE-I WATER SUPPLY SCHEME |  |  | BILL/02569/2024-2025 | BP-239 | 04/02/2025 | 04/02/2025 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 5.72 | 0 | 0 | 0
17 | NADIA | Ranaghat-II | Eastern Mechanical | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | New Service connection charges for Raynagar zone-II water supply scheme |  |  | BILL/02570/2024-2025 | BP-240 | 05/02/2025 | 05/02/2025 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 5.34 | 0 | 0 | 0
18 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Leave Permission For Using Railway Land For Laying Water Main 250 mm Dia (I.D). M.S. carrier pipe line passing through 600 mm (I.D) M.S. casing pipe line under Railway Track from MAST NO:- 77/23, 77/25 and Mast No:- 77/24, 77/26 in between Bankimnagar Halt ( BNKA )- Panchberia Halt ( PNCB ). |  |  | BILL/00546/2024-2025 | 476/PFMS | 17/03/2025 | 17/03/2025 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.58 | 0 | 0 | 0
19 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14234 | New | Duttaphulia-Aranghata Road from CH. 40.00 Km. to CH. 44.766 Km. Restoration estimate due to the cause of excavations for underground Water Supply pipeline layout Proposal of PHE along the R/S of Quality Control sub-Division-I, under Nadia Highway Division-I, in the District Nadia during 2023-2024. |  |  | BILL/00622/2024-2025 | 495/PFMS | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 23.36 | 0 | 0 | 0
Total | [13 empty] | 1442.56 | 8.41 | 0.58