## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300/100/200/200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials , Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 300/100/200/200 m3 Staging Height 20 Mtr, CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length), 2nd T/W Site(50.0 m length)], Pump House for H/W Site(5.4 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) , Land Development and aliied works with Approach Road (105.0m Length and 3.0m Wide), RESTORATION WORK FOR BITUMINOUS ROAD, Hijuli (Zone-I,II,III & IV) Ground Water Based Piped Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000225/2023-2024 | 2351/NAD-I | 03/10/2023 | 02/10/2025 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 1541.25 | 0 | 0 | 3
2 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Preparation of Detailed Project Report (DPR) for Hijuli Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.04) | Assistant Engineer-I | Junior Engineer-IV | ORD/000180/2022-2023 | 39 /NAD-I | 17/01/2023 | 01/02/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 14.36 | 14.25 | 99.27 | 100
3 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2024 to 31/01/2025) | Assistant Engineer-I | Junior Engineer-IV | ORD/000249/2024-2025 | 228/AE-I/NAD-I | 24/07/2024 | 24/01/2025 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
4 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 31.88 | 0 | 0 | 0
5 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Ranaghat -Aranghata (Old) Road from Ch. 0.75 Km. to ch. 12.11 Km. (R.H.S.) "Restoration work arising out of damage of Carriage way & hard shoulder for laying of DI pipeline for integrated surface water based PWSS for Ranaghat -I & Ranaghat-II block under Nadia Arsenic Division-I, PHE Dte" under Nadia Highway Division No.-II, in the District of Nadia during the year of 2024-2025. |  |  | BILL/00332/2024-2025 | 363/PFMS | 17/12/2024 | 17/12/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 57.95 | 0 | 0 | 0
6 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) |  |  | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 06/06/2025 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0 | 0
7 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) |  |  | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 07/09/2025 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0 | 0
8 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) |  |  | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 12/07/2025 | TARUN GHOSH | 89.24 | 0 | 0 | 0
9 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000069/2025-2026 | 530/NAD-I | 03/07/2025 | 01/06/2026 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 78
10 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | Assistant Engineer-I | Junior Engineer-IV | ORD/000287/2024-2025 | 14/AE-I/NAD-I | 30/01/2025 | 30/07/2025 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
11 | NADIA | Ranaghat-II | Eastern Mechanical | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Providing Boundary Illumination with allied works at Hijuli under Block_ Ranaghat-II Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14243) | Assistant Engineer |  | ORD/000170/2025-2026 | 1168/EMD | 04/06/2025 | 02/09/2025 | SHRESTHA | 4.34 | 0 | 0 | 0
12 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 16/11/2025 | BIDYUT KUMAR | 182.15 | 0 | 0 | 0
13 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Shifting of Manifold and interconnection between old and new OHR and revamping /upgradation of hydraulic parameter in the distribution network at bhayna (P) paschim harin danga and hijuli part In connection with hijuli PWSS under Nadia Arsenic Division I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000107/2025-2026 | 721/NAD-I | 29/07/2025 | 27/09/2025 | TAPU SAHA | 51.24 | 0 | 0 | 0
14 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Balance Work for revamping/upgradation of the hydraulic parameters at distribution network at the part of Satpota and Hijuli (P) in connection with Hijuli PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (Sl. No. 01) |  |  | ORD/000142/2025-2026 | 1044/NAD-I | 25/09/2025 | 24/12/2025 | NISHITH BANERJEE | 36.07 | 0 | 0 | 0
15 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Balance Work for revamping / upgradation of the hydraulic parameters at distribution network towards Chttosali more in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000026/2025-2026 | 156/NAD-I | 28/04/2025 | 29/04/2026 | M/S DIPAK ENTERPRISE | 95.47 | 0 | 0 | 100
16 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. | SM/14243 | New | Repair of different types road under Bagula-I GP, Bagula-II GP Ramanagar GP, Chupria GP Raghunathpur, Hijuli-II GP Hijuli PWSS under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000017/2025-2026 | 128/NAD-I | 22/04/2025 | 22/05/2025 | BUDDHADEV MONDAL | 11.74 | 0 | 0 | 100
Total | [13 empty] | 2510.73 | 14.25 | 0.57