## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Preparation of Detailed Project Report (DPR) for Nasra Water Supply Scheme at Ranaghat-II Block atNadia District under Nadia Arsenic Division-I,P.H.E. Dte. (sl.04) | Assistant Engineer-I | Junior Engineer-IV | ORD/000182/2022-2023 | 38/ NAD-I | 16/01/2023 | 23/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 6.74 | 0 | 0 | 100
2 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 19.27 | 0 | 0 | 0
3 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 294/NAD-I | 28/02/2024 | 28/02/2024 | Resource Division | 16.87 | 0 | 0 | 0
4 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I), Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-II), CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length),2nd T/W Site(45.0 m length),3rd T/W(45.0 m length),4th T/W(45.0 m length)],Pump House for H/W Site(4.88 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) ,Land Development,Restoration of Bituminous Road and aliied works with Approach Road (195.0m Length and 3.0m Wide), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 300 m3 of Height 20 Mtr. for Nasra (Zone-I), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 200 m3 of Height 20 Mtr. for Nasra (Zone-II) and RESTORATION WORK FOR BITUMINOUS ROAD at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I&II) in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000239/2023-2024 | 2381/NAD-I | 06/10/2023 | 05/10/2026 | BIDYUT KUMAR | 804.39 | 0 | 0 | 70
5 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) |  |  | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 27/06/2025 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0 | 0
6 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) |  |  | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 07/09/2025 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0 | 0
7 | NADIA | Ranaghat-II | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000069/2025-2026 | 530/NAD-I | 03/07/2025 | 31/10/2025 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 0
8 | NADIA | Ranaghat-II | Eastern Mechanical | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14244 | New | Providing Boundary Illumination with allied works at Nasra under Block_ Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14244) | Assistant Engineer |  | ORD/000158/2025-2026 | 1157/EMD | 04/06/2025 | 02/09/2025 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
Total | [13 empty] | 1228.94 | 0 | 0