## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Preparation of Detailed Project Report (DPR) for Parbatipur Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(SL.05) | Assistant Engineer-I | Junior Engineer-IV | ORD/000181/2022-2023 | 66 / NAD-I | 20/01/2023 | 27/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 10.97 | 0 | 0 | 100
2 | NADIA | Ranaghat-I | Eastern Mechanical | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I & II (Zone-I and II) under Parbatipur ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. (SM/14422) | Assistant Engineer |  | ORD/000651/2024-2025 | 2688/EMD | 20/11/2024 | 20/12/2024 | GOENKA ENTERPRISE | 47.91 | 0 | 0 | 0
3 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 59/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 33.39 | 0 | 0 | 0
4 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1750/NAD-I | 25/10/2024 | 25/10/2024 | Resource Division | 39 | 0 | 0 | 0
5 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 847/NAD-I | 04/06/2024 | 04/06/2024 | Resource Division | 37.63 | 0 | 0 | 0
6 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil Investigation for the work of construction of 400 cum OHR staging height 20 mtr. Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and construction of Pump House, Boundary Wall, Service Road and other allied Works at Head Work & 2nd site under Jal Jeevan Mission for Parbatipur Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl. NO. 06) | Assistant Engineer-I | Junior Engineer-II | ORD/000094/2023-2024 | 1740/NAD-I | 19/07/2023 | 18/07/2026 | H I ENTERPRISE | 628.88 | 0 | 0 | 61
7 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 400 cum OHR staging height 20 mtr., Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house, Boundary Wall, Service Road and other allied Works at Head work & 2nd site under Jal Jeevan Mission for Parbatipur Zone- I Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000096/2023-2024 | 1743/NAD-I | 19/07/2023 | 18/07/2025 | M/S TARAK CHANDRA PAUL | 633.23 | 0 | 0 | 54
8 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Interconnection of pipeline from manifold to different direction of distrtibution pipeline including laying of balance pipeline and FHTC along with allied works at Nrisinghapur (Chandkuri) under Parbatipur Piped Water Supply Scheme at Parbatipur & Gopalpur Mouzas under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) |  |  | ORD/000052/2025-2026 | 529/NAD-I | 03/07/2025 | 01/10/2025 | CHOWDHURY & CO. | 192.83 | 0 | 0 | 0
9 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Augmentation of pipeline and FHTC including repair of Boundary wall at Saguna, Aluipara & Hijuli Mouzas and Parbatipur & Gopalpur Mouzas under Parbatipur Piped Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) |  |  | ORD/000011/2025-2026 | 123/NAD-I | 22/04/2025 | 21/06/2025 | CHOWDHURY & CO. | 85.69 | 0 | 0 | 0
10 | NADIA | Ranaghat-I | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/14422 | New | Laying of pipeline for functionally of FHTC including new FHTC connection at Phuliapara, Durlav para, Narasinghanagar, Chapatala & Beharia Mouza under Fulia G.P. & Gopalpur & Parbatipur mouza under Parbatipur PWSS under Nadia Arsenic Division-I, P.H.E. Dte. (2nd Call) [Sl. No. 04] |  |  | ORD/000101/2025-2026 | 664/NAD-I | 21/07/2025 | 18/11/2025 | BUDDHADEV MONDAL | 87.35 | 0 | 0 | 0
Total | [13 empty] | 1796.88 | 0 | 0