## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Saguna Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15542 | Augmentation | Augmentation of AIRP capacity (78cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Saguna, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.11) | Assistant Engineer-I | Junior Engineer-II | ORD/000140/2023-2024 | 1903/NAD-I | 14/08/2023 | 13/09/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 141.34 | 0 | 0 | 100
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Saguna Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15542 | Augmentation | Providing Boundary Illumination with allied works at Saguna under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15542) | Assistant Engineer |  | ORD/000161/2025-2026 | 1159/EMD | 04/06/2025 | 02/09/2025 | DEEP ENTERPRISE | 4.32 | 0 | 0 | 0
Total | [13 empty] | 145.67 | 0 | 0