## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15544 | Augmentation | Construction and installation of MANIFOLD including UPVC pipeline and allied works at OHR site under Boalia Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. " | Assistant Engineer-I | Junior Engineer-II | ORD/000272/2023-2024 | 2745/NAD-I | 08/12/2023 | 25/02/2025 | MS MAA BHABANI ENTERPRISE | 20.18 | 5.31 | 26.34 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15544 | Augmentation | Augmentation of AIRP capacity (123cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Boalia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-II | ORD/000130/2023-2024 | 1898/NAD-I | 14/08/2023 | 31/08/2025 | M/S R.K. ENTERPRISE | 170.25 | 0 | 0 | 75
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15544 | Augmentation | Providing Boundary Illumination with allied works at Boalia Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | Assistant Engineer |  | ORD/000165/2025-2026 | 1162/EMD | 04/06/2025 | 02/09/2025 | BIJAN ENTERPRISE | 4.33 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15544 | Augmentation | Providing Boundary Illumination with allied works at Gayeshpur Zone II Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | Assistant Engineer |  | ORD/000168/2025-2026 | 1166/EMD | 04/06/2025 | 02/09/2025 | TALUKDER & CO. | 4.34 | 0 | 0 | 0
Total | [13 empty] | 199.1 | 5.31 | 2.67