## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Augmentation Work at Umapur and Goalpur Mouzas at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.04) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000157/2023-2024 | 2115/NAD-I | 04/09/2023 | 19/09/2023 | BUDDHADEV MONDAL | 50.03 | 38.63 | 77.22 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Goalpur Zone-II, Ground Based Water Supply Scheme under Santipur under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte.in connection with Augmentation under JJM under Goalpur Zone-II, Part-III, Piped Water Supply Scheme (Sl.No.-35) | Assistant Engineer-I | Junior Engineer-II | ORD/000110/2023-2024 | 1772/NAD-I | 26/07/2023 | 10/08/2023 | MANISHIKA CONSTRUCTION | 13.04 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Interconnection inbetween new pump to rising main line , Pathway & delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-II water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000201/2023-2024 | 450/AE-I/NAD-I | 29/09/2023 | 29/10/2023 | CONSTRUCTURE | 4.83 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Dedicated line at Dhakuria and delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-I water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000202/2023-2024 | 451/AE-I/NAD-I | 29/09/2023 | 29/10/2023 | M/S G.M ASSOCIATES | 4.82 | 0 | 0 | 100
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II under Goalpur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001768/2023-2024 | 6392/EMD | 30/10/2023 | 29/11/2023 | ASHUTOSH DAS & CO. | 11.76 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 10/05/2025 | BALAJI UDDYOG | 129.1 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Providing Boundary Illumination with allied works at Goalpur Zone II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15546) | Assistant Engineer |  | ORD/000169/2025-2026 | 1167/EMD | 04/06/2025 | 02/09/2025 | SHRESTHA | 4.34 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 30/08/2026 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15546 | Augmentation | Construction of Contact Tank for Conversion of IEP to AIRP at Goalpur PWSS under Shantipur Block under Nadia Arasenic Division-I, P.H.E.Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000031/2024-2025 | 233/AE-I/NAD-I | 25/07/2024 | 30/01/2025 | SATYABRATA CHAKRABORTY | 3.37 | 0 | 0 | 100
Total | [13 empty] | 288.56 | 38.63 | 13.39