## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nabla Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15547 | Augmentation | Augmentation of AIRP capacity (30cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nabla, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000127/2023-2024 | 1885/NAD-I | 11/08/2023 | 21/04/2026 | APURBA MANDAL | 89.6 | 89.6 | 100 | 38
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nabla Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15547 | Augmentation | Providing Boundary Illumination with allied works at Nabla Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15547) |  |  | ORD/000156/2025-2026 | 1156/EMD | 04/06/2025 | 02/09/2025 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
Total | [13 empty] | 93.94 | 89.6 | 95.38