## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte.. | SM/15548 | Augmentation | Augmentation of AIRP capacity (71cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000120/2023-2024 | 1795/NAD-I | 31/07/2023 | 30/08/2023 | ASIT PRAMANIK | 93.55 | 0 | 0 | 42
Total | [13 empty] | 93.55 | 0 | 0