## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Beharia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15549 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I | Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 27/05/2023 | DEBASISH DEY | 12.2 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Beharia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15549 | Augmentation | Augmentation of AIRP capacity (119cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Beharia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (sl.no.01) | Assistant Engineer-I | Junior Engineer-II | ORD/000136/2023-2024 | 1880/NAD-I | 10/08/2023 | 09/09/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 158.74 | 0 | 0 | 100
Total | [13 empty] | 170.93 | 0 | 0