## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15550 | Augmentation | "Retrofitting work at villages Batangachi, Barajiakur and Bagdiain connection with Retrofitting of Ground Water Based PWSS for Goibindapur Zone-II at Santipur Block under Nadia Arsenic Division-I,PHE Dte."(Sl.no.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000071/2023-2024 | 1380/NAD-I | 15/05/2023 | 07/09/2026 | SAHA ENGINEERS | 60.15 | 0 | 0 | 26
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15550 | Augmentation | Augmentation of AIRP capacity (121cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-II, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte (Sl.no.01) | Assistant Engineer-I | Junior Engineer-II | ORD/000141/2023-2024 | 2029/NAD-I | 23/08/2023 | 14/03/2025 | MONDAL PRECISION PRIVATE LIMITED | 173.98 | 140.05 | 80.5 | 35
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15550 | Augmentation | Providing Boundary Illumination with allied works at Gobindapur Zone-II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15550) | Assistant Engineer |  | ORD/000150/2025-2026 | 1152/EMD | 04/06/2025 | 02/09/2025 | M/S DAS ENTERPRISE | 4.34 | 0 | 0 | 0
Total | [13 empty] | 238.47 | 140.05 | 58.73