## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15551 | Augmentation | Augmentation of AIRP capacity (86cum/hr ) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Joypur under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte.(Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000129/2023-2024 | 1886/NAD-I | 11/08/2023 | 10/09/2023 | APURBA MANDAL | 139.79 | 44.73 | 32 | 32
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15551 | Augmentation | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) |  |  | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 06/06/2025 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15551 | Augmentation | Balance Work for revamping / upgradation of the hydraulic parameters at distribution network towards Chttosali more in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) |  |  | ORD/000026/2025-2026 | 156/NAD-I | 28/04/2025 | 27/06/2025 | M/S DIPAK ENTERPRISE | 95.47 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15551 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 05/12/2025 | REAL TIME | 39.28 | 0 | 0 | 50
Total | [13 empty] | 367.66 | 44.73 | 12.17