## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15552 | Augmentation | Augmentation of AIRP capacity (60cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000138/2023-2024 | 1969/NAD-I | 21/08/2023 | 20/09/2023 | B.M. ENGINEERING & CONSTRUCTION | 112.08 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15552 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Muchiphulbari, Dhakuria & Baranberia Mouza in connection with Itaberia PWSS & Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000033/2025-2026 | 167/NAD-I | 29/04/2025 | 27/10/2025 | MS MAA BHABANI ENTERPRISE | 95.54 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15552 | Augmentation | Supply, delivery and installation commissioning of Domestic Ultrasonic (153 RWM) type water meter with Software for data communication at Patkabari, Hatibhanda, Madna, Jaganath, Sahapur & Dhakuria village under augmentation of ground watwer based PWSS for Itaberia W/S Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000015/2025-2026 | 131/NAD-I | 22/04/2025 | 21/06/2025 | SHANTA COLIBRI (INDIA) PVT. LTD. | 5.43 | 0 | 0 | 0
Total | [13 empty] | 213.05 | 0 | 0