## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | Augmentation | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 17/12/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | Augmentation | Laying of pipeline including FHTC connections near Nirsinghapur Health Centre at Nirsinghapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000054/2024-2025 | 248/AE-I/NAD-I | 20/09/2024 | 20/10/2024 | TUHIN CONSTRUCTION | 0.96 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | Augmentation | Laying of pipeline at Nirsinghapur Utterpara including water connection at Nirsinghapur High School and allied works under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer-I | Junior Engineer-II | ORD/000053/2024-2025 | 247/AE-I/NAD-I | 20/09/2024 | 20/10/2024 | TUHIN CONSTRUCTION | 0.97 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | Augmentation | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I | Junior Engineer-II | ORD/000131/2023-2024 | 1899/NAD-I | 14/08/2023 | 05/07/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 0 | 70
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | SM/15553 | Augmentation | Providing Boundary Illumination with allied works at Nrisinghapur Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15553) | Assistant Engineer |  | ORD/000160/2025-2026 | 1158/EMD | 04/06/2025 | 02/09/2025 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
Total | [13 empty] | 221.47 | 0 | 0