## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Preparation of Detailed Project Report (DPR) for Integrated Surface Water Based PWSS for Ranaghat-I & Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-IV | ORD/000116/2023-2024 | 1610/NAD-I | 22/06/2023 | 07/07/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 57.65 | 57.65 | 100 | 100
2 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1085/NAD-I | 25/04/2023 | 25/04/2023 | Resource Division | 1599.91 | 0 | 0 | 0
3 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1887/NAD-I | 11/08/2023 | 11/08/2023 | Resource Division | 1117.16 | 0 | 0 | 0
4 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1874/NAD-I | 10/08/2023 | 10/08/2023 | Resource Division | 1012.08 | 0 | 0 | 0
5 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-31 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00132/2023-2024 | 146/PFMS | 04/07/2023 | 04/07/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 6.15 | 0 | 0 | 0
6 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-49 in IR-RBCS is pending for payment. |  |  | BILL/00191/2023-2024 | 179/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.15 | 0 | 0 | 0
7 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00438/2023-2024 | 345/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
8 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-49 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00278/2023-2024 | 221/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 9.96 | 0 | 0 | 0
9 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-32 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00131/2023-2024 | 147/PFMS | 04/07/2023 | 04/07/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.91 | 0 | 0 | 0
10 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-52 in IR-RBCS is pending for payment. |  |  | BILL/00194/2023-2024 | 177/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
11 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-50 in IR-RBCS is pending for payment. |  |  | BILL/00192/2023-2024 | 178/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.22 | 0 | 0 | 0
12 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00442/2023-2024 | 349/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.32 | 0 | 0 | 0
13 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Taherpur flag to Badkulla station railway crossing for JJM works under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00273/2023-2024 | 220/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.25 | 0 | 0 | 0
14 | NADIA | Ranaghat-I,Ranaghat-II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Earnest money for new service connection at Ranaghat GLR-1 of integrated surface water based PWSS. |  |  | BILL/01919/2023-2024 | BP-126-23-24 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0 | 0
15 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00441/2023-2024 | 348/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
16 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00439/2023-2024 | 346/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
17 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-50 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00279/2023-2024 | 240/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 14.94 | 0 | 0 | 0
18 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Shifting of Electric Pole from the proposed GLR Site inside the Campus of water Management Research Station, Begopara (Patuli) Ranaghat-II Block, under Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00506/2023-2024 | 396/PFMS | 18/12/2023 | 18/12/2023 | WBSEDCL | 0.06 | 0 | 0 | 0
19 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-51 in IR-RBCS is pending for payment. |  |  | BILL/00193/2023-2024 | 180/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.3 | 0 | 0 | 0
20 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-51 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00381/2023-2024 | 340/PFMS | 13/11/2023 | 13/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 19.06 | 0 | 0 | 0
21 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00440/2023-2024 | 347/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
22 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Supply of documents for way leave permission from the Eastern Railways authority at 2 nos of locations on Ranaghat-Krishnagar, Ranaghat -Shantipur&Ranaghat-Bongaon Railway track under Intregrated surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. Intersection Name: 1) AV24- AV28 Birnagar Rail Gate) 2) AV61- AV64 Taherpur Rail Gate) | Assistant Engineer-I | Junior Engineer-I | ORD/000114/2023-2024 | 309/AE-I/NAD-I | 28/07/2023 | 26/10/2023 | SUMAN CHAKRABORTY | 3.84 | 3.84 | 100 | 100
23 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Name of Work: Supply of documents for way leave permission from the Eastern Railways authority at 9 nos of locations on Ranaghat- Krishnagar, Ranaghat- Shantipur & Ranaghat-Bongaon Railway track under Intregrated Surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-IV | ORD/000236/2023-2024 | 2343/NAD-I | 03/10/2023 | 28/10/2023 | SATYABRATA CHAKRABORTY | 17.28 | 17.28 | 100 | 100
24 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Pond side earth protection with Eucalyptus bullah piling at Kamgachi GLR Site within Ranaght-II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000303/2023-2024 | 96/AE-I/NAD-I | 27/02/2024 | 13/03/2024 | R R ENTERPRISE | 4.38 | 4.25 | 97.13 | 100
25 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00565/2023-2024 | 442/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 20.56 | 0 | 0 | 0
26 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00563/2023-2024 | 439/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
27 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00564/2023-2024 | 441/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.93 | 0 | 0 | 0
28 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00562/2023-2024 | 438/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
29 | NADIA | Ranaghat-I,Ranaghat-II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | New Service Connection and security deposit for new bulk power supply at Kamgachi Zone-I W/S Scheme. |  |  | BILL/04121/2023-2024 | BP-258-23-24 | 29/12/2023 | 29/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 43.18 | 0 | 0 | 0
30 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00561/2023-2024 | 437/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.35 | 0 | 0 | 0
31 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | SHIFTING OF POLE AT GANGNAPUR PHE |  |  | BILL/00124/2024-2025 | 100/PFMS | 11/07/2024 | 11/07/2024 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 0.41 | 0 | 0 | 0
32 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Laying of DI Rising Main of Ranaghat I & II Block, Construction of 4 Nos. 100 Cum GLR, 1 No 50 Cum GLR, Construction of 900, 500, 150& 2 Nos. 1500 M3 OHR at Different Location, 6 Nos. Chlorine Room & 5 Nos. Pump House of Integrated Surface Water Based PWSS for Ranaghat-I and Ranaghat-II Block under Nadia Arsenis Division-I P.H.E. Dte (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-IV | ORD/000135/2023-2024 | 1897/NAD-I | 14/08/2023 | 13/08/2026 | AMAL DUTTA ROY | 3770.77 | 809.9 | 21.48 | 90
33 | NADIA | Ranaghat-I,Ranaghat-II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Providing Electro-Mechanical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement for GLR-I at Kamgachi under Surface based Water Supply Scheme for Ranaghat-I Block in the District of Nadia. | Assistant Engineer | Junior Engineer | ORD/001685/2023-2024 | 6260/EMD | 10/10/2023 | 30/06/2025 | WEST BENGAL ENGINEERING CO. | 733.62 | 432.78 | 58.99 | 53
34 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Laying and repairing of damaged UPVC pipeline of different existing piped water supply schemes under PHED at Ranaghat-I & II Block due to laying of DI Secondary Rising main under Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block, including restoration of village roads by Jhama Metal, Rail/National Way Crossing of pipeline, Pipe Carriage and allied works Under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000174/2024-2025 | 1748/NAD-I | 24/10/2024 | 21/07/2025 | AMAL DUTTA ROY | 474.38 | 0 | 0 | 80
35 | NADIA | Ranaghat-I,Ranaghat-II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Carriage of DI pipes including Pipe carrying structure, road restoration, repair of damaged UPVC pipeline, crossing of pipeline by jack pushing, pathway and allied works related to Integrated Surface Water Based Water Supply Scheme under Ranaghat-I & II Blocks under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) |  |  | ORD/000111/2025-2026 | 786/NAD-I | 12/08/2025 | 10/12/2025 | AMAL DUTTA ROY | 559.99 | 0 | 0 | 0
Total | [13 empty] | 9498.75 | 1325.69 | 13.96