## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 29 Nos. distribution zone for Chakdah (Part) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte (Sl.no 01) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000166/2023-2024 | 2110/NAD-I | 01/09/2023 | 01/03/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 8630 | 1017.68 | 11.79 | 10
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Chakdah (Part) in the district of Nadia. |  |  | ORD/001636/2023-2024 | 6193/EMD | 05/10/2023 | 05/04/2024 | G.B. CONSTRUCTION | 615.17 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS for Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000123/2023-2024 | 1829/NAD-I | 07/08/2023 | 22/08/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 74.61 | 74.61 | 100 | 100
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Supply, delivery & installation of Rotary Assembly for Horizontal split case pump at Chakdah WTP, Pump No.-V, under Eastern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001775/2023-2024 | 6399/EMD | 30/10/2023 | 28/01/2024 | ORIENTAL ENGINEERING CO. | 9.85 | 9.85 | 100 | 100
5 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1884/NAD-I | 11/08/2023 | 11/08/2023 | Resource Division | 3612.51 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Construction of pathway and allied works for WTP Chakdah in connection with Augmentation of Chakdah WTP under JJM within Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000064/2024-2025 | 1709/NAD-I | 21/10/2024 | 11/11/2024 | MALI CONSTRUCTION | 39.68 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Restoration of damages pipelines at PWD Bridge at Raninagar village in Balagorichar (Zone-XII) under augmentation of surface water based PWSS for Chakdah Part at Chakdah Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000005/2024-2025 | 143/AE-II/NAD-I | 07/06/2024 | 03/05/2025 | MESSRS FREEDOM CONSTRUCTION | 4.05 | 3.75 | 92.51 | 100
8 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1952/NAD-I | 28/11/2024 | 28/11/2024 | Resource Division | 38.55 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Continuation work order of Casual hiring of vehicle on an as and when required basis for Jal-Jeevan Mission site inspection under Nadia arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000255/2024-2025 | 500/AE-II/NAD-I | 28/03/2025 | 28/09/2025 | BUDDHADEV MONDAL | 0.86 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/18661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 88/NAD-I | 16/04/2025 | 16/04/2025 | Resource Division | 119.32 | 0 | 0 | 0
Total | [13 empty] | 13144.6 | 1105.89 | 8.41