## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 26 Nos. distribution zone for Haringhata & Chakdah (Part) in Haringhata & Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000279/2023-2024 | 2730/NAD-I | 07/12/2023 | 02/05/2027 | G.B. CONSTRUCTION & UMWELT JV | 10913.55 | 2891.16 | 26.49 | 3
2 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS fo Haringhata & Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000246/2023-2024 | 2614/NAD-I | 22/11/2023 | 07/12/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 92.86 | 92.86 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Augmentation work of Clariflocculator-I of Haringhata & Chakdah (Part) WTP (33.39) MLD under JJM in connection with Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) at Chakdah & Haringhata block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000261/2023-2024 | 2699/NAD-I | 05/12/2023 | 26/12/2023 | G.B. CONSTRUCTION | 95.48 | 95.14 | 99.65 | 100
4 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Augmentation of different units in connection with augmentation of Surface Based PWSS for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (sl.03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000269/2023-2024 | 2610/NAD-I | 22/11/2023 | 22/12/2023 | CHOWDHURY & CO. | 95.73 | 95.45 | 99.71 | 100
5 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Interconnection between outlet pipe of OHR and delivery main at different H/W sites in Haringhata and Chakdah (Part) surface water based PWSS at Haringhata block in connection with JJM under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000067/2024-2025 | 1710/NAD-I | 21/10/2024 | 11/11/2024 | TARUN KUMAR BHATTACHARYA | 36.87 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Haringhata & Chakdah (Part) in the District of Nadia. | Assistant Engineer | Junior Engineer | ORD/000037/2024-2025 | 1523/EMD | 07/06/2024 | 07/12/2024 | G.B. CONSTRUCTION | 592.09 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Augmentation work of Filter Bed & different units of Haringhata & Chakdah (Part) WTP (33.39 MLD) under JJM in connection with augementation of Surface Water Based W/S Scheme for Haringhata &Chakdah (Part) at Chakdah & Haringhata Block in the didtrict of Nadia under Nadia Arsenic Division - I P. H.E. Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000282/2023-2024 | 08/NAD-I | 03/01/2024 | 28/01/2024 | TARUN KUMAR BHATTACHARYA | 24.29 | 24.17 | 99.53 | 100
8 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Emergency restoration of UPVC pipeline for functionally of FHTC connections, damaged due to restoration of roads at Nagar Ukhra ¿I & II G.P. at Haringhata Block of Surface Water Based PWSS for Zone-II (Hapania) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000063/2024-2025 | 1494/NAD-I | 18/09/2024 | 01/05/2025 | MONDAL ENTERPRISE | 25.84 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 2054/NAD-I | 09/12/2024 | 09/12/2024 | Resource Division | 112.27 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2090/NAD-I | 16/12/2024 | 16/12/2024 | Resource Division | 207.24 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1167/NAD-I | 29/07/2024 | 29/07/2024 | Resource Division | 438.24 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 276/NAD-I | 23/02/2024 | 23/02/2024 | Resource Division | 250.42 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Shifting and relaying of distribution pipeline under Haringhata-Chakdah(P) Zone-III from pond side to inner location for preventing bacteriological contamination of distribution water and providing secondary chlorination system and including internal electrification and yard lighting at all the 13 (thirteen) nos of existing zones of Surface Water based water supply schemes for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000248/2024-2025 | 2804/NAD-I | 25/03/2025 | 09/05/2025 | TARUN KUMAR BHATTACHARYA | 35.7 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Augmentation of WTP & Intake in all respect along with ancillary works to make all the units, SCADA compatible all complete at Chakdah WTP under Augmentation of Chakdah Part & Haringhata & Chakdah (Part) under Nadia Arsenic Division I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000022/2025-2026 | 97/NAD-I | 17/04/2025 | 15/08/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 855.87 | 0 | 0 | 0
15 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Replacing of old filter media from filter bed and supply, placing by new filter media of different size, Replacing the control chamber of the filter bed , construction of shed over filter bed & installation of SCADA system and ancillary works at HARINGHATA WTP under Augmentation of HARINGHATA & CHAKDAH(Part) under Nadia Arsenic Division I, PHE Dte. (sl.02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000023/2025-2026 | 96/NAD-I | 17/04/2025 | 15/08/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 839.8 | 0 | 0 | 0
16 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 2436/NAD-I | 06/02/2025 | 06/02/2025 | Resource Division | 40.59 | 0 | 0 | 0
17 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-III-B/1 (Hazrapota) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005358688) |  |  | BILL/01936/2025-2026 |  | 08/09/2025 | 08/09/2025 | WBSEDCL NAGARUKHRA CCC | 10.96 | 0 | 0 | 0
18 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-VIII-C (Alaipur) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005392316) |  |  | BILL/02157/2025-2026 |  | 09/10/2025 | 09/10/2025 | W.B.S.E.D.C.LTD (MADANPUR C.C.C) | 4.79 | 0 | 0 | 0
19 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-IX-B (Kalyani) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005314899) |  |  | BILL/01897/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL KALYANI CCC, | 5.71 | 0 | 0 | 0
20 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-XI-B (Chanduria) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005392091) |  |  | BILL/02158/2025-2026 |  | 09/10/2025 | 09/10/2025 | W.B.S.E.D.C.LTD (MADANPUR C.C.C) | 4.17 | 0 | 0 | 0
21 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-VIII-B (Shikarpur) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005392425) |  |  | BILL/02159/2025-2026 |  | 09/10/2025 | 09/10/2025 | W.B.S.E.D.C.LTD (MADANPUR C.C.C) | 8.27 | 0 | 0 | 0
22 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-I-B (Haripukuria) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005359394) |  |  | BILL/01899/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL SUBARNAPUR C.C.C. | 9.07 | 0 | 0 | 0
23 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-II-C (Simulpukuria) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005358652) |  |  | BILL/01933/2025-2026 |  | 08/09/2025 | 08/09/2025 | WBSEDCL NAGARUKHRA CCC | 5.13 | 0 | 0 | 0
24 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-III-C (Sekenderpur) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005345538) |  |  | BILL/01846/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL NAGARUKHRA CCC | 15.19 | 0 | 0 | 0
25 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-V-B (Parmajdia) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005392379) |  |  | BILL/02160/2025-2026 |  | 09/10/2025 | 09/10/2025 | W.B.S.E.D.C.LTD (MADANPUR C.C.C) | 7.95 | 0 | 0 | 0
26 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-X-B (Narayanpur) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005359446) |  |  | BILL/01901/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL SUBARNAPUR C.C.C. | 7.24 | 0 | 0 | 0
27 | NADIA |  | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | New Service connection charges for SILINDA W/S SCHEME |  |  | BILL/00602/2024-2025 |  | 25/03/2025 | 25/03/2025 | WBSEDCL EAST BISHNUPUR CCC | 9.91 | 0 | 0 | 0
28 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-III-B/2 (Utter Brahamapur) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005358680) |  |  | BILL/01935/2025-2026 |  | 08/09/2025 | 08/09/2025 | WBSEDCL NAGARUKHRA CCC | 3.99 | 0 | 0 | 0
29 | NADIA |  | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. | SM/19042 | Augmentation | WBSEDCL Quotation for New Service Connection to the Head Work Site of Zone-IV-B (Mollaberia) for newly OHR constructing under Surface Water Based Water Supply Scheme under Haringhata & Chakdaha (Part), P.H.E. Dte., Dist.- Nadia. (Application No. 3005359237) |  |  | BILL/01898/2025-2026 |  | 02/09/2025 | 02/09/2025 | WBSEDCL SUBARNAPUR C.C.C. | 10.39 | 0 | 0 | 0
Total | [13 empty] | 14759.6 | 3198.78 | 21.67