## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of Chemical and reagents at water testing laboratory at Haringhata WTP under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000265/2023-2024 | 538/AE-I/NAD-I | 11/12/2023 | 10/01/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
2 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of glassware and consumable at water testing laboratory at Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000262/2023-2024 | 536/AE-I/NAD-I | 11/12/2023 | 10/01/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.95 | 0.95 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation work for 6(Six) months maintenance contract (only service & preventative maintenance along with software support) after expiry of one year performance warranty of the offered system at Haringhata water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Government of West Bengal. (Period from 1/1/2024 to 30/06/2024) | Assistant Engineer-I | Junior Engineer-I | ORD/000286/2023-2024 | 551/AE-I/NAD-I | 27/12/2023 | 27/06/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.1 | 2.1 | 100 | 100
4 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of different chemical and accessories for Haringhata WTP Water Testing Laboratory (Prandhara) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-I | ORD/000291/2023-2024 | 29/AE-I/NAD-I | 19/01/2024 | 03/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
5 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Renovation of existing laboratory room for installation of ICPMS & IC including sample preparation room and Gas cylinder storage room & UPS room along with allied electrical and sanitary works at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000297/2023-2024 | 168/NAD-I | 07/02/2024 | 22/02/2024 | TARUN KUMAR BHATTACHARYA | 10.43 | 10.17 | 97.51 | 100
6 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply and installation of LED Sign Board along with other allied electrical works at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000300/2023-2024 | 91/AE-I/NAD-I | 22/02/2024 | 23/03/2024 | TARUN KUMAR BHATTACHARYA | 4.83 | 4.82 | 99.63 | 100
7 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation work for "Operation, Analysis, Application support & Training for Triple Quadrupole GC-MS/MS system by engaging Resource Person/s for Pesticide Residue Analysis of Water at Haringhata Water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, PHE Dte, Government of West Bengal for a period of six (6) months. (w.e.f. 03/03/2024 to 02/09/2024)" | Assistant Engineer-I | Junior Engineer-I | ORD/000334/2023-2024 | 103/AE-I/NAD-I | 01/03/2024 | 01/09/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.46 | 3.46 | 100 | 100
8 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation work for 6(Six) months maintenance contract (only service & preventative maintenance along with software support) after expiry of one year performance warranty of the offered system at Haringhata water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Government of West Bengal. (Period from 1/07/2024 to 31/12/2024) | Assistant Engineer-I | Junior Engineer-I | ORD/000019/2024-2025 | 203/AE-I/NAD-I | 28/06/2024 | 29/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.1 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of Argan (XL) Cylinder for running ICP-MS & IC at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000011/2024-2025 | 191/AE-I/NAD-I | 21/06/2024 | 06/07/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.98 | 0.98 | 100 | 100
10 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of Chemical & Certified Reference Materials at Kalyani State Laboratory under Nadua Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000013/2024-2025 | 193/AE-I/NAD-I | 21/06/2024 | 06/07/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.95 | 0.95 | 100 | 100
11 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation Work Order for Deployment of Laboratory Personal at the laboratory under Haringhata WTP (Sub-district laboratory for Prandhara) at Kalyani, Nadia. (Period from 01.04.2024 to 30.09.2024) | Assistant Engineer-I | Junior Engineer-I | ORD/000018/2024-2025 | 130/AE-I/NAD-I | 01/04/2024 | 01/10/2024 | DULAL MAJUMDER | 3.83 | 3.62 | 94.61 | 100
12 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation Work Order for Deployment of Laboratory Personal at the laboratory under Haringhata WTP (Sub-district laboratory for Prandhara) at Kalyani, Nadia. (Period from 01.10.2024 to 31.03.2025) | Assistant Engineer-I | Junior Engineer-I | ORD/000114/2024-2025 | 254/AE-I/NAD-I | 01/10/2024 | 01/04/2025 | DULAL MAJUMDER | 3.83 | 3.83 | 100 | 100
13 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation work for "Operation, Analysis, Application support & Training for Triple Quadrupole GC-MS/MS system by engaging Resource Person/s for Pesticide Residue Analysis of Water at Haringhata Water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, PHE Dte, Government of West Bengal for a period of six (4) months. (w.e.f. 03/09/2024 to 31/12/2024)" | Assistant Engineer-I | Junior Engineer-I | ORD/000061/2024-2025 | 241/AE-I/NAD-I | 02/09/2024 | 02/01/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.25 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Acceptance & Workorder Continuous monitoring and testing of water samples by supply of Chemical References and Consumable Gases (As and When Required) for analysing of water samples by ICMS-IC & GCMS at Kalyani State Referral Laboratory under Nadia Arsenic Division-I,PHE Dte for period of 1 Year. (1.09.24 to 31.08.25) | Assistant Engineer-I | Junior Engineer-I | ORD/000075/2024-2025 | 1284/NAD-I | 13/08/2024 | 13/08/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 16.23 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Supply of different Certified Reference Material (CRM) etc for maintaining Quality Standard as per ISO:17025-2017 at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000179/2024-2025 | 348/AE-I/NAD-I | 26/12/2024 | 25/01/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.96 | 0.96 | 100 | 100
16 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuous monitoring and testing of water samples by supply of Chemical References and Consumable Gases (As and When Required) for analysing of water samples by ICPMS & GCMS at Kalyani State Referral Laboratory under Nadia Arsenic Division-I,PHE Dte for period of 1 Year. (Sl. NO. 01) |  |  | ORD/000185/2025-2026 | 1200/NAD-I | 18/11/2025 | 18/11/2026 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 16.15 | 0 | 0 | 0
17 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Operation , analysis , Application support, training and maintenance and service of GC- MS/MS System including engagement of resource personnel at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte (WEF- 01/01/2025 to 31/12/2025) | Assistant Engineer-I | Junior Engineer-I | ORD/000190/2024-2025 | 2270/NAD-I | 06/01/2025 | 06/01/2026 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 11.38 | 0 | 0 | 100
18 | NADIA |  | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19079 | Support-WQMSP | Continuation Work Order for Deployment of Laboratory Personal at the laboratory under Haringhata WTP (Sub-district laboratory for Prandhara) at Kalyani, Nadia. (Period from 01.04.2025 to 30.09.2025) | Assistant Engineer-I | Junior Engineer-I | ORD/000272/2024-2025 | 54/AE-I/NAD-I | 24/03/2025 | 23/09/2025 | DULAL MAJUMDER | 3.83 | 0 | 0 | 100
Total | [13 empty] | 86.2 | 33.78 | 39.19