## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. | SM/19098 | Augmentation | Providing pumping machinery and electrical equipment for secondary Boosting station at different OHR sites in Ranaghat-II block in connection with integrated surface water based PWSS in the Dist. of Nadia , P.H.E, Dte. |  |  | ORD/002634/2023-2024 | 312/EMD | 07/02/2024 | 07/08/2024 | A.G ENTERPRISE. | 110.43 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. | SM/19098 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR RANAGHAT-II GLR (PATULI) |  |  | BILL/00738/2024-2025 | BP-54-24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 69.14 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. | SM/19098 | Augmentation | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement at Ranaghat-II Block GLR Site of surface water based water supply scheme, Arsenic Affected Area, in the district of Nadia, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/002489/2023-2024 | 83/EMD | 11/01/2024 | 01/01/2026 | WEST BENGAL ENGINEERING CO. | 852.36 | 0 | 0 | 25
Total | [13 empty] | 1031.93 | 0 | 0