## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Fatepur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000068/2020-2021 | 07/NACD-II | 05/01/2021 | 21/03/2021 | MITRA CONSTRUCTION | 50.76 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | Retrofitting | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Bansberia W/S scheme. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000008/2020-2021 | 1144/NACD-II | 03/11/2020 | 03/12/2020 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.8 | 4.8 | 99.86 | 0
3 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | Retrofitting | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Khanjipur W/S scheme. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000007/2020-2021 | 1143/NACD-II | 03/11/2020 | 03/12/2020 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.79 | 4.79 | 99.99 | 0
4 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District | SM/07300 | Retrofitting | Name of work:-Rejuvenate the existing media of pressure filtter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Chandpur W/S scheme. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000009/2020-2021 | 1145/NACD-II | 03/11/2020 | 03/12/2020 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.83 | 4.83 | 99.99 | 0
Total | [13 empty] | 65.17 | 14.41 | 22.11