## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000193/2021-2022 | 985/NACD-II | 27/12/2021 | 27/03/2022 | SUPRITI ENTERPRISE | 111.19 | 111.18 | 99.99 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Change of Media of AIRP at Damodarkhali H/W site under Damodarkhali W/S scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000093/2022-2023 | 36/AE-I/NACD-II | 02/05/2022 | 12/05/2022 | RUPALI ELECTRONICS | 4.93 | 4.93 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | RESOURCE PAYMENT DAMODARKHALI |  |  | VCH/000888/2021-2022 | 257 | 26/03/2022 | 26/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 20.38 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  |  | VCH/000643/2021-2022 |  | 05/01/2022 | 05/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. |  |  | VCH/000718/2021-2022 | 212, 213, 214 | 18/01/2022 | 18/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | RESOURCE PAYMENT DAMODARKHALI |  |  | VCH/000889/2021-2022 | 256 | 26/03/2022 | 26/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 33.72 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  |  | VCH/000646/2021-2022 |  | 07/01/2022 | 07/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000029/2021-2022 | 522/NACD-II | 14/06/2021 | 29/07/2021 | SHYAMAL SHIL | 51.46 | 40.46 | 78.62 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or daaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000141/2021-2022 | 569/NACD-II | 14/07/2021 | 28/08/2021 | SHYAMAL SHIL | 6.11 | 6.11 | 100 | 100
10 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 15/04/2023 | M.S. ENTERPRISE | 65.68 | 5.87 | 8.94 | 90
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 955/NACD-II | 14/12/2021 | 14/12/2021 | Resource Division | 64.9 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Damodarkhali Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000065/2024-2025 | 711/NACD-II | 07/06/2024 | 22/07/2024 | GHOSH ENTERPRISE | 19.1 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.16 | 0.01 | 6.93 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2023-2024 | 37/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 20.2 | 20.12 | 100
Total | [13 empty] | 889.28 | 188.76 | 21.23