## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000129/2021-2022 | 868/NACD-II | 08/11/2021 | 23/12/2021 | SANJOY BAKSHI | 62.77 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Construction of Boundary wall with Grill Gate at Taldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000265/2021-2022 | 50/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | GHOSH ENTERPRISE | 4.04 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Rejuvanation of Taldaha W/ Scheme in krishnaganj block nadia under EMSD-III Phe Dte. | Assistant Engineer | Junior Engineer | ORD/000693/2021-2022 | 231/EMD | 15/02/2022 | 15/09/2022 | ABHISEK ENGINEERING CONCERN | 7.43 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Goari, Gopipur & Mathurapur) Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000344/2022-2023 | 145/NACD-II | 17/01/2023 | 06/02/2023 | CHANDRA NATH GHOSH | 2.27 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000293/2022-2023 | 1191/NACD-II | 23/12/2022 | 07/01/2023 | BABLU MALLICK | 1.13 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection including laying of pipeline at Taldaha Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000245/2023-2024 | 21/AE-II/NACD-II | 15/02/2024 | 01/03/2024 | SHYAMAL SHIL | 0.97 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001777/2022-2023 | 1122/EMD | 16/03/2023 | 15/04/2023 | ANJAN ENTERPRISE | 46.98 | 0 | 0 | 80
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Taldaha PWSS (Capacity- 43 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000200/2023-2024 | 90/NACD-II | 18/01/2024 | 18/03/2024 | MONDAL PRECISION PRIVATE LIMITED | 94.35 | 0 | 0 | 99
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Wall writing work in various Gram Panchayats in Krishnaganj Block at Taldaha PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000047/2024-2025 | 758/AE-I/NACD-II | 19/06/2024 | 04/07/2024 | IMAGIN | 0.93 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.53 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Taldaha) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000088/2024-2025 | 867/NACD-II | 04/07/2024 | 25/07/2024 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 79/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000222/2021-2022 | 52/NACD-II | 20/01/2022 | 06/03/2022 | B.M. ENGINEERING & CONSTRUCTION | 27.75 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | Retrofitting | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2024-2025 | 1571/NACD-II | 06/12/2024 | 02/09/2025 | BIDYUT KUMAR | 105.92 | 0 | 0 | 40
Total | [13 empty] | 367.12 | 0 | 0