## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000124/2021-2022 | 857/NACD-II | 08/11/2021 | 23/12/2021 | S.K. CONSTRUCTION | 95.18 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-III W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000299/2022-2023 | 1197/NACD-II | 23/12/2022 | 07/01/2023 | SUMIT GHOSH | 1.61 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 15/04/2023 | M.S. ENTERPRISE | 65.68 | 0 | 0 | 90
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-III Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000243/2023-2024 | 19/AE-II/NACD-II | 15/02/2024 | 01/03/2024 | M/S SREE KRISHNA ENTERPRISE. | 0.97 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Helenchi Z-III PWSS (Capacity- 49 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000256/2023-2024 | 233/NACD-II | 21/02/2024 | 21/04/2024 | B.M. ENGINEERING & CONSTRUCTION | 96.32 | 0 | 0 | 5
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2024-2025 | 1571/NACD-II | 06/12/2024 | 02/09/2025 | BIDYUT KUMAR | 105.92 | 0 | 0 | 40
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Repair and Renovation work at Helenchi Zone - III HeadWork site in Krishnaganj Block with Overhead Reservoir with Plaster,Painting and other allied works under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000236/2024-2025 | 1377/NACD-II | 04/10/2024 | 31/01/2025 | TAPAN SAHA | 7.56 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | Retrofitting | Repair and Renovation work at Helenchi Zone - III H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000017/2024-2025 | 139/AE-II/NACD-II | 11/06/2024 | 08/01/2025 | BASUDEB SAHA | 3.56 | 0 | 0 | 100
Total | [13 empty] | 376.96 | 0 | 0