## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Construction of Path Way & Earth filling at H/w site of Bahirgachhi Zone-II Piped Water Supply Scheme under NACD - II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000239/2021-2022 | 81//AE-I/NACD-II | 27/08/2021 | 11/09/2021 | SHYAMAL SHIL | 2.77 | 2.77 | 99.9 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000274/2021-2022 | 874/NACD-II | 09/11/2021 | 24/12/2021 | CHAKRABORTTY ENTERPRISE | 17.84 | 17.65 | 98.91 | 100
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Rejuvenation of Bahirgachi Zone-II W/S Scheme in chapra block of Nadia, W/O-473/EMD, T.no.06/EMD | Assistant Engineer | Junior Engineer | ORD/000258/2021-2022 | 473/EMD | 16/03/2022 | 15/04/2022 | DAS ENTERPRISE | 6.02 | 6.02 | 100 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000134/2020-2021 | 274/EE/NACD-II | 22/02/2021 | 15/03/2021 | SOMNATH CHATTERJEE | 30.67 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000098/2021-2022 | 736/NACD-II | 13/09/2021 | 28/10/2021 | CHAKRABORTTY ENTERPRISE | 50.01 | 50 | 99.97 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000128/2021-2022 | 863/NACD-II | 08/11/2021 | 23/12/2021 | IJABUL SEKH | 60.77 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-II W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000371/2022-2023 | 350/NACD-II | 22/03/2023 | 11/04/2023 | SAMARESH GHOSH | 0.78 | 0.78 | 99 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II (Vill-Mirgipota,Choruitipi) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000258/2022-2023 | 1013/NACD-II | 29/11/2022 | 13/01/2023 | GHOSH & CO. | 9.65 | 9.15 | 94.74 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000166/2023-2024 | 1294/NACD-II | 23/11/2023 | 14/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000172/2023-2024 | 1302/NACD-II | 29/11/2023 | 20/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 2.95 | 50 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000361/2023-2024 | 35/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 24.76 | 24.63 | 80
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-II W/S Scheme of Chapra Block Mouza Ramnagar & Mrigipota of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000211/2023-2024 | 612/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | MALLICK ENTERPRISE | 0.97 | 0.48 | 49.69 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | Retrofitting | Repair and Renovation work at Bahirgachi Zone-II 2nd Tube Well Site under Bahirgachi Zone-II Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000201/2024-2025 | 899/AE-I/NACD-II | 10/09/2024 | 10/10/2024 | M/S FREEDOM CONSTRUCTION | 3.96 | 0 | 0 | 0
Total | [13 empty] | 295.77 | 120.44 | 40.72