## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bansbaria (Vill- Poragachha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000225/2020-2021 | 288/NACD-II | 23/02/2021 | 16/03/2021 | SANDIP BISWAS | 35.39 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair due to construction of road) at Bansbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000264/2022-2023 | 1019/NACD-II | 29/11/2022 | 28/01/2023 | S.B. CONSTRUCTION | 27.03 | 27.03 | 99.98 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Bansberia) |  | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000092/2023-2024 | 1058/NACD-II | 20/09/2023 | 11/10/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
4 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 15/04/2023 | M.S. ENTERPRISE | 65.68 | 5.87 | 8.94 | 90
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Renovation work at Bansberia Head Work Site under Bansberia Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000228/2024-2025 | 926/AE-I/NACD-II | 30/09/2024 | 30/10/2024 | JYOTIRMOY ENTERPRISE | 4.61 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Bansberia PWSS (Capacity- 31 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000199/2023-2024 | 89/NACD-II | 18/01/2024 | 18/03/2024 | MONDAL PRECISION PRIVATE LIMITED | 78.06 | 74.16 | 95 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Repair and Renovation work at Bansberia 2nd tube well Site under Bansberia Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000340/2024-2025 | 1055/AE-I/NACD-II | 19/12/2024 | 15/04/2025 | GAUTAM HALDER | 3.7 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | Retrofitting | Supply of Water Level Indicator at Bansberia in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000413/2024-2025 | 1158/AE-I/NACD-II | 31/01/2025 | 17/03/2025 | M/S S.K. CONSTRUCTION | 0.77 | 0 | 0 | 100
Total | [13 empty] | 221.14 | 112.96 | 51.08