## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha (Vill- Bhagaban pur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000291/2020-2021 | 297./NACD-II | 25/02/2021 | 12/03/2021 | M/S. ASIT KUMAR BISWAS | 4.67 | 2.14 | 45.89 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000302/2021-2022 | 734./NACD-II | 13/09/2021 | 28/10/2021 | M/S K.P. CONSTRUCTION | 50.23 | 50.12 | 99.78 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000309/2021-2022 | 109/AE-II/NACD-II | 04/03/2022 | 09/03/2022 | MAKALI ENGINEERING CORPORATION | 4.98 | 4.98 | 100 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000317/2021-2022 | 113/AE-II/NACD-II | 10/03/2022 | 15/03/2022 | MAKALI ENGINEERING CORPORATION | 4.93 | 4.93 | 100 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Construction of Boundary wall with Grill Gate at Sakdaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000249/2021-2022 | 107/NACD-II | 10/02/2022 | 27/03/2022 | SAMAR ENTERPRISE | 5.63 | 5.34 | 94.86 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Sakdaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000294/2022-2023 | 1192/NACD-II | 23/12/2022 | 07/01/2023 | M/S. ASIT KUMAR BISWAS | 1.33 | 1.27 | 95.74 | 100
7 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000009/2023-2024 | 1507/EMD | 18/04/2023 | 18/05/2023 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 33.2 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Sakdaha Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000064/2023-2024 | 322_2/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | RISHAN ENGINEERING CONSULTANCY | 0.71 | 0.71 | 100 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Sakdaha Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000246/2023-2024 | 23/AE-II/NACD-II | 15/02/2024 | 27/09/2024 | SHYAMAL SHIL | 0.97 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Sakdaha Water Supply Scheme of capacity 30 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000307/2023-2024 | 423/NACD-II | 15/03/2024 | 12/11/2025 | JOY GOPAL GUPTI | 84.47 | 16.11 | 19.07 | 82
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Additional work for the Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000054/2024-2025 | 162/AE-II/NACD-II | 14/06/2024 | 29/06/2024 | M/S. ASIT KUMAR BISWAS | 0.51 | 0.5 | 99.72 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Sakdaha) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000086/2024-2025 | 863/NACD-II | 03/07/2024 | 24/07/2024 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Providing of Hydraulic Connectivity in the Left out habitations at sakdaha water supply scheme as per IS Code 10500:2012 in the Block of Krishnaganj, Nadia Under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2024-2025 | 129/AE-II/NACD-II | 10/06/2024 | 25/06/2024 | SHYAMAL SHIL | 4.85 | 4.81 | 99.14 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Provisioning of Har Ghar Jal an Integral Component of Jal Jeevan Mission with necessary addition and alteration at sakdaha water supply scheme in the Krishnagar Sadar Sub Division, Nadia under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000030/2024-2025 | 130/AE-II/NACD-II | 10/06/2024 | 25/06/2024 | SHYAMAL SHIL | 4.83 | 4.81 | 99.42 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Construction of Remote Segment Components of some of the pipe water supply schemes in Sakdaha water supply scheme Under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000031/2024-2025 | 131/AE-II/NACD-II | 10/06/2024 | 23/09/2024 | SHYAMAL SHIL | 4.84 | 4.83 | 99.8 | 100
16 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Repair and Renovation work at Sakdaha H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting , and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000016/2024-2025 | 138/AE-II/NACD-II | 11/06/2024 | 29/12/2024 | BABLU MALLICK | 3.96 | 3.31 | 83.69 | 100
17 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Continuation work order for Construction of Remote Segment Components of some of the pipe water supply schemes in Sakdaha water supply scheme Under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000424/2024-2025 | 243/AE-II/NACD-II | 31/07/2024 | 15/08/2024 | SHYAMAL SHIL | 2.81 | 0 | 0 | 100
18 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.53 | 0.1 | 19.56 | 100
19 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Repair and Renovation work at Sakdaha Head Work site in Krishnaganj Block with Overhead Reservoir with Plaster, Painting, and other allied works under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000226/2024-2025 | 1358/NACD-II | 30/09/2024 | 30/10/2024 | EVEREST CONSULTANT SERVICES. | 6.29 | 6.24 | 99.3 | 100
20 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | Augmentation | Acceptance cum Work Order "Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at the new proposed sites of Sakdah Zone-I and Zone-II in Krishnaganj Block under Sakdah Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. Alternate Site - Thanapara Zone-II 2nd T/w Site, Maliapota, Patharghata." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000032/2025-2026 | 570/NACD-II | 08/05/2025 | 01/08/2026 | B.M. ENGINEERING & CONSTRUCTION | 21.67 | 0 | 0 | 40
Total | [13 empty] | 228.81 | 120.99 | 52.88