## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000203/2021-2022 | 191/AE-I/NACD-II | 29/12/2021 | 23/01/2022 | PRABIR KUMAR ROY | 4.81 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Raising the height of Boundary wall at H/W site and also Construction of Soak Pit at Lakshmipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000024/2022-2023 | 03/AE-I/NACD-II | 06/04/2022 | 21/05/2022 | PRABIR KUMAR ROY | 5 | 2.37 | 47.37 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000306/2021-2022 | 281/AE-I/NACD-II | 04/03/2022 | 09/03/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.94 | 4.94 | 100 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-I (Vill- Shimlibas) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000086/2021-2022 | 627/NACD-II | 10/08/2021 | 25/08/2021 | M/S TARUN GHOSH & CO. | 4.51 | 4.51 | 99.86 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000319/2021-2022 | 303/AE-I/NACD-II | 17/03/2022 | 22/03/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.9 | 4.9 | 100 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur (Vill- Kalyandaha, Lakshmipur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000259/2022-2023 | 1014/NACD-II | 29/11/2022 | 28/01/2023 | PRABIR KUMAR ROY | 17.93 | 17.87 | 99.65 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Restoration of damaged distribution pipe line and parallel pipeline laying due to construction of PMGSY Road and Extension of Boundary Wall at Lakshmipur (Vill-Kalyandaha) Head Work Site W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000265/2022-2023 | 1020/NACD-II | 29/11/2022 | 29/12/2022 | PRADIP KUMAR BANIK | 4.85 | 4.81 | 99.16 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Lakshmipur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000096/2023-2024 | 1116/NACD-II | 06/10/2023 | 27/10/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Conversion of IEP to AIRP at Laksmipur Water Supply Scheme of capacity 60 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000214/2024-2025 | 1308/NACD-II | 20/09/2024 | 19/11/2024 | JOY HIND TUBEWELLS | 165.22 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Lakshmipur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000069/2023-2024 | 325/1/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | SIRCON ENGINEERING SERVICE | 1.11 | 1.1 | 99.52 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000125/2021-2022 | 858/NACD-II | 08/11/2021 | 23/12/2021 | M/S GHOSH CONSTRUCTION | 82.39 | 82.36 | 99.97 | 100
Total | [13 empty] | 301.55 | 128.75 | 42.7