## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Hiring of Diesel SUV car for office use of the Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte. Krishnagar, Nadia. for the period 01.11.2022 to 31.03.2023.(Five months) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000356/2022-2023 | 785//NACD-II | 28/10/2022 | 28/03/2023 | TARUN KUMAR BHATTACHARYA | 2.07 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000183/2022-2023 | 164/AE-I/NACD-II | 28/07/2022 | 28/10/2022 | JOY GOPAL GUPTI | 4.75 | 4.75 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagberia) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000097/2023-2024 | 1117/NACD-II | 06/10/2023 | 27/10/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 910/NACD-II | 24/11/2021 | 24/11/2021 | Resource Division | 7.39 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 133 | 25/02/2022 | 25/02/2022 | Resource Division | 92.34 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000290/2023-2024 | 197/NACD-II | 12/02/2024 | 12/05/2024 | SINGHA ROY & CO. | 159.46 | 4.75 | 2.98 | 30
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000339/2023-2024 | 597/AE-I/NACD-II | 29/01/2024 | 13/02/2024 | PARTHA DAS | 0.91 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Bagberia Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000067/2023-2024 | 324/1/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | SIRCON ENGINEERING SERVICE | 1.21 | 0.98 | 80.85 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000186/2023-2024 | 532/AE-I/NACD-II | 18/12/2023 | 02/01/2024 | SUBHANKAR ROY | 0.97 | 0.93 | 96.19 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Karmakar Para and HajraPara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000223/2023-2024 | 623/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | SHYAMAL KANTI GHOSH | 0.93 | 0.92 | 99.89 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Schoolpara ,Hatpara, Christanpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte¿ | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000224/2023-2024 | 624/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | SREE GURU ENTERPRISE | 0.93 | 0.86 | 92.32 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Muslimpara and Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000219/2023-2024 | 619/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | SUBHANKAR ROY | 0.93 | 0.89 | 95.03 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000225/2023-2024 | 625/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | NIVEDITA CONSTRUCTION | 0.91 | 0.89 | 97.82 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Daspara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000222/2023-2024 | 622/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | BINOY DAS | 0.93 | 0.91 | 98.56 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Masjidpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000220/2023-2024 | 620/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | SHOVON KUMAR MODAK | 0.97 | 0.93 | 96.13 | 100
16 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Clubpara and Dilar Para &Rajbangsi Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dt | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000221/2023-2024 | 621/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | NAMDAR ALI | 0.97 | 0.84 | 87.32 | 100
17 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000218/2023-2024 | 618/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | ST. ANTHONY ENTERPRISE | 0.96 | 0.88 | 92.34 | 100
18 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Gajantala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000338/2023-2024 | 596/AE-I/NACD-II | 29/01/2024 | 13/02/2024 | BK ENGINEERING | 0.91 | 0.91 | 99.68 | 100
19 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Quotation for load enhancement and security deposit charges at PH-I of Bagberia PWSS,Nadia |  |  | BILL/02079/2024-2025 | BP-169-24-25 | 05/12/2024 | 05/12/2024 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.46 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bagberia Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000332/2024-2025 | 1582/NACD-II | 11/12/2024 | 07/09/2025 | SANDIP BISWAS | 111.44 | 0 | 0 | 75
21 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | Augmentation | Repair and Renovation work at Bagberia 2nd tube well Site under Bagberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000347/2024-2025 | 1024/AE-I/NACD-II | 10/12/2024 | 09/01/2025 | M/S FREEDOM CONSTRUCTION | 4.76 | 0 | 0 | 0
Total | [13 empty] | 403.1 | 25.35 | 6.29