## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000139/2021-2022 | 866/NACD-II | 08/11/2021 | 23/12/2021 | TAPU SAHA | 51.28 | 47 | 91.65 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000095/2021-2022 | 733/NACD-II | 13/09/2021 | 28/10/2021 | USHA CONSTRUCTION | 66.93 | 66.91 | 99.96 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Drawal of HT OH power line incld. errection of PCC pole inst. of electrical Transformer & supply of materials under supervision of WBSEDCL for new service connection at PH- II under Nischintapur w/s scheme NACD II under EMD PHE dte | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 4426/ EMD | 30/06/2021 | 30/06/2022 | ABHISEK ENGINEERING CONCERN | 1.08 | 1.08 | 100 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Construction of Soak Pit and land development and also concrete road construction for smooth movement within OHR site at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000255/2021-2022 | 36/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | A.K ADHIKARY | 4.99 | 4.98 | 99.79 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Construction of Boundary wall with Grill Gate at Nischintapur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000264/2021-2022 | 49/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | NAMDAR ALI | 4.56 | 4.54 | 99.72 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Reparing of vertical distribution line and also renovation of inside of OHR at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000138/2022-2023 | 454/NACD-II | 14/07/2022 | 13/08/2022 | A.K ADHIKARY | 4.92 | 4.92 | 99.91 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Laying of D.I. Pipeline as rising main from 2nd Tube Well Site to head work site and also construction of column for supporting the pipeline at Nischintapur Water Supply Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000271/2022-2023 | 1082/NACD-II | 09/12/2022 | 08/01/2023 | SUPER CONSTRUCTION | 7.15 | 5.75 | 80.48 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000170/2023-2024 | 1299/NACD-II | 29/11/2023 | 20/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Nischintapur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000061/2023-2024 | 321_1/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | SIRCON ENGINEERING SERVICE | 1.43 | 1.43 | 99.94 | 100
10 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PUTIMARI(Block-Tehatt-I), NISCHINTAPUR(Block-Tehatt-I), W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 1504/EMD | 18/04/2023 | 18/05/2023 | SRI KRISHNA NIRMAN | 10.69 | 5.24 | 49 | 80
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) |  |  | ORD/000171/2023-2024 | 1301/NACD-II | 29/11/2023 | 20/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Nischintapur Water Supply Scheme of capacity 62 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000318/2023-2024 | 216/NACD-II | 16/02/2024 | 12/04/2025 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 207.27 | 203.13 | 98 | 72
13 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | Augmentation | Quotation for load enhancement of power supply at PH-I of Nischintapur W/S scheme ,under EMSD-III, PHE Dte., Nadia |  |  | BILL/02017/2024-2025 | BP-163-24-25 | 25/11/2024 | 25/11/2024 | W.B.S.E.D.C.L (TEHATTA CCC) | 4.34 | 0 | 0 | 0
Total | [13 empty] | 376.45 | 350.87 | 93.21