## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Maheshpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000033/2021-2022 | 526/NACD-II | 14/06/2021 | 29/07/2021 | TARUN GHOSH | 66.44 | 132.76 | 199.83 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chenderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000094/2021-2022 | 732/NACD-II | 13/09/2021 | 28/10/2021 | SINGHA ROY & CO. | 65.96 | 131.79 | 199.81 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase -I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipe line (Parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur(Vill- Pukura) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000081/2021-2022 | 641/NACD-II | 13/08/2021 | 27/09/2021 | NILAY KUMAR BHATTACHARYA | 59.57 | 119.1 | 199.95 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000313/2021-2022 | 859/EE/NACD-II | 08/11/2021 | 23/12/2021 | PRIYA CONSTRUCTION | 53.27 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000108/2021-2022 | 766/NACD-II | 22/09/2021 | 06/11/2021 | SANDIP BISWAS | 84.78 | 169.54 | 199.98 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Gongra W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2023-2024 | 438/NACD-II | 12/04/2023 | 02/05/2023 | BIPLAB BHOWMICK | 1.47 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000137/2021-2022 | 859/NACD-II | 08/11/2021 | 23/12/2021 | PRIYA CONSTRUCTION | 53.27 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000284/2023-2024 | 176/NACD-II | 07/02/2024 | 07/04/2024 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Gongra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000060/2023-2024 | 320_2/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | SIRCON ENGINEERING SERVICE | 1.29 | 1.29 | 100 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at new proposed site of Gongra Zone-I and Zone-II in Chapra Block under Gongra Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000317/2024-2025 | 1527/NACD-II | 27/11/2024 | 24/08/2025 | SANDIP BISWAS | 21.68 | 0 | 0 | 55
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 25/12/2025 | CHANDAN ROY | 149.25 | 0 | 0 | 20
Total | [13 empty] | 734.77 | 554.47 | 75.46