## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000112/2021-2022 | 477/NACD-II | 07/05/2021 | 17/05/2021 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 200 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000113/2021-2022 | 488/NACD-II | 13/05/2021 | 23/05/2021 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 200 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Supply and installation of Corona Guard (Brand- Eureka Forbes)(6 nos) and disinfection work at different office chambers at Nadia arsenic Civil Division-II, PHE Dte. Krishnagar, Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000290/2020-2021 | 312/NACD-II | 05/03/2021 | 10/03/2021 | ABHISEK ENGINEERING CONCERN | 4.91 | 9.82 | 200 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000026/2021-2022 | 519/NACD-II | 14/06/2021 | 29/07/2021 | M/S SHILL & CO. | 55.01 | 75.3 | 136.89 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Work of Survery, Design, Drawing & DPR preparation for CHANDPUR Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000009/2021-2022 | 3/AE-I/NACD-II | 06/05/2021 | 13/05/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.92 | 5.84 | 200 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-III Water Supply Scheme in KRISHNAGANJ Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000011/2021-2022 | 5/AE-I/NACD-II | 06/05/2021 | 13/05/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 4.29 | 8.58 | 200 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-II Water Supply Scheme in KRISHNAGANJ Block of Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000012/2021-2022 | 6/AE-I/NACD-II | 06/05/2021 | 13/05/2021 | UMWELT ENGINEER PVT LTD. | 3.15 | 6.3 | 200 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for BAHIRGACHHI ZONE-II Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2021-2022 | 1/AE-I/NACD-II | 06/05/2021 | 13/05/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.66 | 5.31 | 200 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for BANSBERIA Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000008/2021-2022 | 2/AE-I/NACD-II | 06/05/2021 | 13/05/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.94 | 5.87 | 200 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000109/2021-2022 | 767/NACD-II | 22/09/2021 | 06/11/2021 | JOY HIND TUBEWELLS | 94.04 | 188.28 | 200.2 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-II) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-III ( Village- Bhajanghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000077/2021-2022 | 16/AE-II/NACD-II | 13/08/2021 | 28/08/2021 | SUMIT GHOSH | 4.96 | 9.9 | 199.36 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Special repairing works of damaged old pipe line at Brittihuda including anciliary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000121/2021-2022 | 136/AE-I/NACD-II | 28/10/2021 | 12/11/2021 | JOY HIND TUBEWELLS | 5 | 10 | 200 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000100/2021-2022 | 737/NACD-II | 13/09/2021 | 28/10/2021 | M/S ANUBHAB CONSTRUCTION | 62.35 | 124.69 | 199.97 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Refixing of existing ferrule connection broken due to heavy vehicular traffic including road restoration work at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000076/2021-2022 | 15/AE-II/NACD-II | 13/08/2021 | 23/08/2021 | JOY HIND TUBEWELLS | 3.43 | 6.85 | 199.86 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Digri (Vill- Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000087/2021-2022 | 687/NACD-II | 03/09/2021 | 13/09/2021 | M/S RAJESH CONSTRUCTION | 4.99 | 9.97 | 199.62 | 100
16 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Barnia (Vill- Avaynagar) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000107/2021-2022 | 130/AE-I/NACD-II | 14/09/2021 | 29/09/2021 | M/S FREEDOM CONSTRUCTION | 4.5 | 8.99 | 199.82 | 100
17 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Repair and Renovation work at Tengra 2nd tube well Site under Tengra Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000328/2024-2025 | 1025/AE-I/NACD-II | 10/12/2024 | 09/01/2025 | SHOVON KUMAR MODAK | 4.05 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Tengra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000059/2023-2024 | 320_1/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0.47 | 55.32 | 100
19 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 29/11/2024 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Laying of 75mm dia pipeline alongwith FHTC reconnection Tengra W/S Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000441/2024-2025 | 1204/AE-I/NACD-II | 27/02/2025 | 13/04/2025 | ASHIM ENTERPRISE | 0.96 | 0 | 0 | 0
21 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | Augmentation | Laying of 75mm dia pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000442/2024-2025 | 1205/AE-I/NACD-II | 27/02/2025 | 13/04/2025 | JOY HIND TUBEWELLS | 0.97 | 0 | 0 | 100
Total | [13 empty] | 436.59 | 495.1 | 113.4