## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Providing Functional House Hold Tap Connection(Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10mm dia gun-Metal ferrule,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline(parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000127/2020-2021 | 271/EE/NACD-II | 22/02/2021 | 15/03/2021 | SANDIP BISWAS | 52.44 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2020-2021 | 190/NACD-II | 15/02/2021 | 08/03/2021 | SANDIP BISWAS | 36.12 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000131/2021-2022 | 870/NACD-II | 08/11/2021 | 23/12/2021 | BIDYUT KUMAR | 34.62 | 34.61 | 99.99 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000263/2021-2022 | 46/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | R.M. TRADING | 4.97 | 4.97 | 99.9 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000296/2021-2022 | 112/NACD-II | 11/02/2022 | 12/05/2022 | MONDAL ENTERPRISE | 45.84 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000123/2022-2023 | 59/AE-II/NACD-II | 28/06/2022 | 28/07/2022 | R.M. TRADING | 2.74 | 2.72 | 99.48 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | New pipeline laying by providing 200 mm dia D.I. pipe over existing columns to cross the PWD Bridge and PVC pipe for supplying water to Khalboalia village under krishnaganj Block and also Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at ( Vill- Khalboalia) Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000178/2022-2023 | 520/NACD-II | 05/08/2022 | 04/10/2022 | SANJIB DEY | 96.93 | 96.88 | 99.95 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Shyamnagar W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000301/2022-2023 | 1199/NACD-II | 23/12/2022 | 07/01/2023 | R.M. TRADING | 0.89 | 0.83 | 93.89 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Construction of RCC Column for supporting pipeline for future extension ( Near Khalbualia Bridge) alongwith Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000137/2022-2023 | 453/NACD-II | 14/07/2022 | 28/08/2022 | SANJIB DEY | 8.58 | 8.51 | 99.17 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Shyamnagar Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000066/2023-2024 | 323_2/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | SIRCON ENGINEERING SERVICE | 2.29 | 2.01 | 87.82 | 100
11 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. |  |  | ORD/001482/2023-2024 | 1505/EMD. | 18/04/2023 | 18/05/2023 | DIPALI CONSTRUCTION | 19.37 | 6.37 | 32.86 | 80
12 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 1505/EMD | 18/04/2023 | 18/05/2023 | DIPALI CONSTRUCTION | 19.37 | 0 | 0 | 90
13 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Shyamnagar Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000248/2023-2024 | 25/AE-II/NACD-II | 15/02/2024 | 01/03/2024 | SUMIT GHOSH | 0.97 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Shyamnagar Water Supply Scheme of capacity 67 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000286/2023-2024 | 185/NACD-II | 09/02/2024 | 09/04/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 194.41 | 194.41 | 100 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 nonmagnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Shyamnagar PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000311/2024-2025 | 362/AE-II/NACD-II | 19/11/2024 | 26/11/2024 | PUNGENT ENGINEERING PVT LTD | 0.98 | 0.98 | 100 | 100
16 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Quotation for load enhancement at Pump House No-I of Shyamanagar (Krishnaganj Block) w/s scheme under EMSD-III,PHE Dte.,Nadia |  |  | BILL/01328/2024-2025 | BP-73-24-25 | 30/07/2024 | 30/07/2024 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.44 | 0 | 0 | 0
17 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000416/2024-2025 | 09/NACD-II | 06/02/2025 | 07/05/2025 | SUMIT GHOSH | 105.58 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Relaying of rising main and other necessary allied works at Shyamnagar Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2025-2026 | 21/AE-I/NACD-II | 11/04/2025 | 10/06/2025 | NISHITH BANERJEE | 3.66 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | New pipeline laying by providing 200 mm dia D.I. pipe over existing columns to cross the PWD Bridge and PVC pipe for supplying water to Khalboalia village under krishnaganj Block and also Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at ( Vill- Khalboalia) Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | BILL/00189/2025-2026 |  | 19/06/2025 | 19/06/2025 | SANJIB DEY | 5.19 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | Augmentation | Construction of RCC Column for supporting pipeline for future extension ( Near Khalbualia Bridge) alongwith Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | BILL/00190/2025-2026 |  | 19/06/2025 | 19/06/2025 | SANJIB DEY | 0.46 | 0 | 0 | 0
Total | [13 empty] | 635.84 | 352.29 | 55.4