## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Construction of Boundary wall with Grill Gate at Bahadurpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000258/2021-2022 | 40/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | TAPAN SAHA | 4.45 | 0 | 0 | 100
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Supply and delivery of PCC Pole, MS material and allied works to WBSEDC Ltd. for Bahadurpur PWSS, W/O-879/EMSD-III, T.No.45/SD-III | Assistant Engineer | Junior Engineer | ORD/000459/2022-2023 | 879/EMSD-III | 29/07/2022 | 28/08/2022 | M/S G.P. ENTERPRISE | 0.75 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Continuation work order for Collection on House Hold Details at prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different PWSS under Nadia Arsenic Civil Division-II, PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000235/2021-2022 | 216/AE-I/NACDII | 01/02/2022 | 06/02/2022 | JOY GOPAL GUPTI | 4.91 | 0 | 0 | 100
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Supply & delivery of PCC pole MS material and allied electrical accessories to WBSEDCL Ltd ( Nazirpur CCC) for Bahadurpur PWSS PH.- II under EMSD III Dist. Nadia | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 879/EMSD III | 29/07/2022 | 02/08/2022 | M/S. G.P. ENTERPRISE | 0.75 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | SUPPLY OF 11 KV AB CABLE & ALLIED ELECTRICAL ACCESSORIES TO WBSEDCL NAZIRPUR CCC FOR BAHADURPUR PWSS |  |  | VCH/000072/2022-2023 | 30 | 26/04/2022 | 26/04/2022 | T. N. BANERJEE | 2.05 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipeline repair) at Krishnagar & Bahadurpur (Vill- Krishnagar, Chak Chilakhali) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000215/2021-2022 | 08/NACD-II | 04/01/2022 | 18/02/2022 | MITRA CONSTRUCTION | 34.08 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000177/2021-2022 | 948/NACD-II | 09/12/2021 | 23/01/2022 | MITRA CONSTRUCTION | 45.4 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bahadurpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000256/2022-2023 | 1011/NACD-II | 29/11/2022 | 28/01/2023 | NAMDAR ALI | 12.93 | 0 | 0 | 90
9 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000009/2023-2024 | 1507/EMD | 18/04/2023 | 18/05/2023 | SWAPAN KUMAR BHANJA | 14.69 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Bahadurpur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000073/2023-2024 | 327/1/AE-I/NACD-II | 13/07/2023 | 20/07/2023 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Bahadurpur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000173/2023-2024 | 1303/NACD-II | 29/11/2023 | 20/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2021-2022 | 867/NACD-II | 08/11/2021 | 23/12/2021 | MITRA CONSTRUCTION | 46.77 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000308/2023-2024 | 424/NACD-II | 15/03/2024 | 09/05/2025 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 0 | 70
14 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Repair and Renovation work at Bahadurpur HW Site & 2nd pump house site with Reinforced Barbed Tape , Flooring ,Plaster ,Painting, Pathway , and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000025/2024-2025 | 148/AE-II/NACD-II | 11/06/2024 | 05/08/2025 | SREE GURU ENTERPRISE | 2.55 | 0 | 0 | 0
15 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 25/12/2025 | CHANDAN ROY | 149.25 | 0 | 0 | 20
16 | NADIA |  | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | Augmentation | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 16/09/2025 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
Total | [13 empty] | 604.27 | 0 | 0