## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Preparation of DPR for augmentation of existing Barnia, (Block -Tehatta-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000149/2021-2022 | 148/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.63 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Preparation of DPR for augmentation of existing Barnia (Phase-II), (Block -Tehatta-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000172/2021-2022 | 751/NACD-II | 15/09/2021 | 25/09/2021 | SIRCON ENGINEERING SERVICE | 4.73 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also DI Laying in distribution at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000211/2021-2022 | 993/NACD-II | 30/12/2021 | 13/02/2022 | J.D.J. ENTERPRISE | 98.17 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000140/2020-2021 | 275/EE/NACD-II | 22/02/2021 | 15/03/2021 | USHA CONSTRUCTION | 51.53 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Restoration by UPVC Pipeline for replacing the damaged pipeline at Barnia Bazar and also construction of RCC slab for at Barnia Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000120/2021-2022 | 135/AE-I/NACD-II | 28/10/2021 | 12/11/2021 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.21 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia (Village- Charakpota) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000142/2021-2022 | 824/NACD-II | 25/10/2021 | 09/12/2021 | JOY HIND TUBEWELLS | 68.53 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Barnia Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000162/2021-2022 | 165/AE-I/NACD-II | 22/11/2021 | 29/11/2021 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Continuation work order for for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000165/2021-2022 | 850/NACD-II | 02/11/2021 | 17/12/2021 | JOY HIND TUBEWELLS | 73.72 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000241/2021-2022 | 98/NACD-II | 10/02/2022 | 27/03/2022 | PRABIR KUMAR ROY | 14.31 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000232/2021-2022 | 982/EE/NACD-II | 27/12/2021 | 10/02/2022 | M/S. R.K.ENTERPRISE | 152.25 | 0 | 0 | 100
Total | [13 empty] | 475.06 | 0 | 0