## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Preparation of DPR for augmentation of existing Brittihuda, (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000146/2021-2022 | 145/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | UMWELT ENGINEER PVT LTD. | 3.89 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Preparation of DPR for augmentation of existing Brittihuda (Phase-II), (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000174/2021-2022 | 757/NACD-II | 16/09/2021 | 26/09/2021 | SIRCON ENGINEERING SERVICE | 4.95 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000191/2021-2022 | 983/NACD-II | 27/12/2021 | 27/03/2022 | IJABUL SEKH | 177.61 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Making of Office Furniture including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000196/2021-2022 | 184/AE-I/NACD-II | 29/12/2021 | 18/01/2022 | SURAJIT KUMAR GHOSH | 4.89 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Rejuvenation of the offiec room including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000197/2021-2022 | 185/AE-I/NACD-II | 29/12/2021 | 18/01/2022 | SURAJIT KUMAR GHOSH | 4.97 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000028/2021-2022 | 521/NACD-II | 14/06/2021 | 29/07/2021 | JOY HIND TUBEWELLS | 74.36 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000073/2021-2022 | 562/NACD-II | 13/07/2021 | 27/08/2021 | JOY HIND TUBEWELLS | 73.59 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Relaying of D.I. Pipeline replacing the damaged old HDPE Rising Main Pipe line at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000123/2021-2022 | 140/AE-I/NACD-II | 01/11/2021 | 16/11/2021 | GOUTAM HALDER | 3.37 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Continuation work order for Special repairing works of damaged old pipe line at Brittihuda including ancillary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000164/2021-2022 | 168/AE-I/NACD-II | 23/11/2021 | 08/12/2021 | JOY HIND TUBEWELLS | 4.99 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000229/2021-2022 | 995/EE/NACD-II | 30/12/2021 | 13/02/2022 | CHANDA CONSTRUCTION | 98.72 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000072/2021-2022 | 547/NACD-II | 07/07/2021 | 21/08/2021 | JOY HIND TUBEWELLS | 73.68 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000119/2021-2022 | 134/AE-I/NACD-II | 28/10/2021 | 12/11/2021 | TAPAS GHOSH | 4.96 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.53 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | Retrofitting | Shifting of 01 no existing 63 KVA, 11/0.4 KV DTR I.R.O PHE Brittihuda PWSS head works site, Brittihuda under Chapra CCC. |  |  | BILL/00216/2024-2025 | 133 | 06/09/2024 | 06/09/2024 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.68 | 0 | 0 | 0
Total | [13 empty] | 531.2 | 0 | 0